## Change History
Document Change History:
Ver.Rel. No | Release date | Modified By | Reviewed By | Approved By' | Remarks

## Requirement Traceability Table
PD-01-02 Ver 2.11 / 25-Jun-04 |  |  | Requirement Traceability Table
Project ID: |  | IAP-001 |  | Project Name: |  | Insurance Agent Portal
Last Updated Date: |  | 2020-07-19
Requirement Traceability Table details:
Req. Id. | Requirement Description | CR.No. | Status | High Level Design Element ID | HLD Version No. | Detailed Level Design Element Id. | DLD Version No. | Program Specification Id. | Program Specification Version No. | Test Case Id. | Test Case Version No. | Program Name or Id. | Program Version No. | Priority | Type | Remarks
Sample
Req-01 | Loan calculator |  | Open | LC | 1 | LC | 1 | [6 empty] | High | Original | Since software is developed as a prototype requirement is not fully functional
Req-02 | A dummy Chat-bot with list of screens in it. |  | Open | CB | 1 | CB | 1 | [6 empty] | Very High | Original | Since software is developed as a prototype requirement is not fully functional
Req-03 | Online Appointment Booking |  | Open | AP | 1 | AP | 1 | [6 empty] | High | Original
Req-04 | Customer payments Page |  | Open | PD | 1 | PD | 1 | [6 empty] | Low | Original
Req-05 | Our Services page |  | Open | SP | 1 | SP | 1 | [6 empty] | Low | Original
Req-06 | Horizantal Slider |  | Open | HS | 1 | HS | 1 | [6 empty] | Medium | Original | Since software is developed as a prototype requirement is not fully functional
Req-07 | News at lower side of the home page |  | Open | NS | 1 | NS | 1 | [6 empty] | Low | Original
Req | Site Resembling AmarBima |  | Open | AB | 1 | AB | 1 | [6 empty] | Very High | Original

## CR-PR Breakup
PD-01-02 Ver 2.11 / 25-Jun-04 |  |  |  | CR-PR Breakup
Project ID: |  |  | Project Name:
Last Updated Date:
CR-PR Breakup details:
CR. No. | Date | Change/ Problem | Change Description | Priority | Accepted / Rejected | Status | Reference

## CR-PR Analysis
PD-01-02 Ver 2.11 / 25-Jun-04 |  |  |  |  | CR-PR Analysis
Project ID: |  |  | Project Name:
Last Updated Date:
CR-PR Analysis details:
CR. No. | Assigned To | Severity | Affected Items | Module Name | Estimated Efforts | Estimated Start Date | Estimated End Date | Actual Efforts | Actual Start Date | Actual End Date | Reviewed By | Remarks