## WAS
PM-01-02 Ver 2.01 / 29-Sep-04 |  |  | Work Allocation Sheet
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Sr. No. | PDLC Stage | Module Name | Work Item / Review Item | Type | Assigned To | Reference file ID / Bug ID | Planned Time in Hours | Planned Start Date | Planned End Date | Actual Time in Hours | Actual Start Date | Actual End Date | Planned Effort (Hrs) | Actual Effort (Hrs) | Number of Resources | Status | Dependencies | Remarks
1 | Requirement | Requirements Checklists | Filling Checklists | core work | TM | P-RC | - | 2020-07-13 | 2020-07-26 | - | 2020-07-13 | 2020-07-23 | 223 | 200 | 6 | Completed | Project Acceptance
2 | Requirement | Requirements Checklists | Review | Review | PL | P-RC | - | 2020-07-14 | 2020-07-27 | - | 2020-07-14 | 2020-07-24 |  |  |  | Completed
3 | Requirement | Documentation of requirements | Documentation | core work | TM | P-DR | - | 2020-07-15 | 2020-07-28 | - | 2020-07-15 | 2020-07-25 |  |  |  | Completed
4 | Requirement | Documentation of requirements | Review | Review | PL | P-DR | - | 2020-07-16 | 2020-07-29 | - | 2020-07-16 | 2020-07-26 |  |  |  | Completed
Estimation Phase
5 | Estimation | Estimation using Function Point Analysis | Filling Documents | core work | TM | P-FP | - | 2020-07-26 | 2020-08-01 | - | 2020-07-24 | 2020-07-28 | 130 | 120 | 6 | Completed | Requirement Documentation
6 | Estimation | Estimation using Function Point Analysis | Review | Review | PL | P-FP | - | 2020-07-27 | 2020-08-02 | - | 2020-07-25 | 2020-07-29 |  |  |  | Completed
7 | Estimation | Estimation using PCM | Filling Documents | core work | TM | P-PM | - | 2020-07-28 | 2020-08-03 | - | 2020-07-26 | 2020-07-30 |  |  |  | Completed
8 | Estimation | Estimation using PCM | Review | Review | PL | P-PM | - | 2020-07-29 | 2020-08-04 | - | 2020-07-27 | 2020-07-31 |  |  |  | Completed
9 | Estimation | Estimation using BS | Filling Documents | core work | TM | P-BS | - | 2020-07-30 | 2020-08-05 | - | 2020-07-28 | 2020-08-01 |  |  |  | Completed
10 | Estimation | Estimation using BS | Review | Review | PL | P-BS | - | 2020-07-31 | 2020-08-06 | - | 2020-07-29 | 2020-08-02 |  |  |  | Completed
Design Phase
13 | Design | Design-HLD using SSAD | HLD | Core work | TM | P-LD |  | 2020-08-10 | 2020-08-16 |  | 2020-08-24 | 2020-08-30 |  | 13.5 | 8 | Completed | Requirement and Estimation Documentation
13.1.1 | Design | Determination of Development Enviornment | Documentation | Core work | Shreyash A. | P-LD-1 | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.1.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.2.1 | Design | Determination of Modular Specification | Documentation | Core work | Varun K. | P-LD-2 | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.2.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.3.1 | Design | Determination of Design Approach | Documentation | Core work | Jitesh M. | P-LD-3 | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.3.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.4.1 | Design | Determination of System Architecture | Documentation | Core work | Simran K. | P-LD-4 | 3 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.4.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 1.5 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.5.1 | Design | Designing HLD | Documentation | Core work | Kartik P. | P-LD-5 | 3 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
13.5.2 | Design | Knowledge Gathering of the Respective Topic |  | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 1.5 | 2020-08-24 | 2020-08-30 |  |  |  | Completed
14 | Design | Design-HLD | Review | Review | PL(Jitesh M.) | P-LD-R | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-08-30 |  |  |  | Planned
15 | Design | Design-DLD | DLD | Core work | TM | P-DD |  | 2020-08-10 | 2020-08-16 | [6 empty] | Planned
16 | Design | Design-DLD | Review | Review | PL | P-DD |  | 2020-08-10 | 2020-08-16 | [6 empty] | Planned
Development Phase
17 | Development | Home Page | Coding | Core work | TM | P-HP |  | 2020-08-17 | 2020-08-23 |  |  |  | 699 |  | 10 | Planned | Requirement, Design and Estimation Documentation
18 | Development | Home Page | Review | Review | PL | P-HP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
19 | Development | About Us | Coding | Core work | TM | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
20 | Development | About Us | Review | Review | PL | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
21 | Development | Our Services | Coding | Core work | TM | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
22 | Development | Our Services | Review | Review | PL | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
23 | Development | Payments | Coding | Core work | TM | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
24 | Development | Payments | Review | Review | PL | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
25 | Development | Contact Us | Coding | Core work | TM | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
26 | Development | Contact Us | Review | Review | PL | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
27 | Development | Chat-Bot | Coding | Core work | TM | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
28 | Development | Chat-Bot | Review | Review | PL | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
29 | Development | Nav-Bar | Coding | Core work | TM | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
30 | Development | Nav-Bar | Review | Review | PL | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
31 | Development | Footer | Coding | Core work | TM | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
32 | Development | Footer | Review | Review | PL | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
33 | Development | Database Management of G-Forms input | Coding | Core work | TM | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
34 | Development | Database Management of G-Forms input | Review | Review | PL | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
35 | Development | Database Management Of Payment Details | Coding | Core work | TM | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
36 | Development | Database Management Of Payment Details | Review | Review | PL | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
37 | Development | Miscellaneous Database Management | Coding | Core work | TM | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
38 | Development | Miscellaneous Database Management | Review | Review | PL | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
Testing Phase
39 | Testing | Home Page | Unit Testing | Core work | TM | P-HP |  | 2020-08-24 | 2020-08-30 |  |  |  | 460 |  | 11 | Planned | Requirement, Design and Estimation Documentation with Developed Software
40 | Testing | Home Page | Review | Review | PL | P-HP |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
41 | Testing | About Us | Unit Testing | Core work | TM | P-AU |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
42 | Testing | About Us | Review | Review | PL | P-AU |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
43 | Testing | Our Services | Unit Testing | Core work | TM | P-OS |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
44 | Testing | Our Services | Review | Review | PL | P-OS |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
45 | Testing | Payments | Unit Testing | Core work | TM | P-PS |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
46 | Testing | Payments | Review | Review | PL | P-PS |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
47 | Testing | Contact Us | Unit Testing | Core work | TM | P-CU |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
48 | Testing | Contact Us | Review | Review | PL | P-CU |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
49 | Testing | Chat-Bot | Unit Testing | Core work | TM | P-CB |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
50 | Testing | Chat-Bot | Review | Review | PL | P-CB |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
51 | Testing | Nav-Bar | Unit Testing | Core work | TM | P-NB |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
52 | Testing | Nav-Bar | Review | Review | PL | P-NB |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
53 | Testing | Footer | Unit Testing | Core work | TM | P-FT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
54 | Testing | Footer | Review | Review | PL | P-FT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
55 | Testing | Database Management of G-Forms input | Unit Testing | Core work | TM | P-DG |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
56 | Testing | Database Management of G-Forms input | Review | Review | PL | P-DG |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
57 | Testing | Database Management Of Payment Details | Unit Testing | Core work | TM | P-DP |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
58 | Testing | Database Management Of Payment Details | Review | Review | PL | P-DP |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
59 | Testing | Miscellaneous Database Management | Unit Testing | Core work | TM | P-MM |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
60 | Testing | Miscellaneous Database Management | Review | Review | PL | P-MM |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
61 | Testing | Integerated Modules | Integration testing | Core work | TM | P-IM-IT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
62 | Testing | Integerated Modules | Review | Review | PL | P-IM-IT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
63 | Testing | Integerated Modules | System Testing | Core work | TM | P-IM-ST |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
64 | Testing | Integerated Modules | Review | Review | PL | P-IM-ST |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
65 | Testing | Integerated Modules | Acceptance Testing | Core work | TM | P-IM-AT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
66 | Testing | Integerated Modules | Review | Review | PL | P-IM-AT |  | 2020-08-24 | 2020-08-30 | [6 empty] | Planned
Deployment Phase
67 | Deployment | Integerated Modules | Publishing site and setting up the database. | Core work | TM | P-IM-PL |  | 2020-08-31 | 2020-09-06 |  |  |  | 195 |  | 8 | Planned | Requirement, Design and Estimation Documentation with Developed Software
68 | Deployment | Integerated Modules | Review | Review | PL | P-IM-PL |  | 2020-08-31 | 2020-09-06 | [6 empty] | Planned
Maintainance Phase
69 | Maintainance | Integerated Modules | Maintainace of the site | Core work | TM | P-IM-MC |  | 2020-09-06 | 2020-12-05 |  |  |  | To be estimated later |  | 10 | Planned | Requirement, Design and Estimation Documentation and Developed Software
70 | Maintainance | Integerated Modules | Review | Review | PL | P-IM-MC |  | 2020-09-06 | 2020-12-05 | [6 empty] | Planned