## Change History
PM-02-01 Ver 1.0 /25-July-20 |  |  |  | Change History
Project ID: |  | IAP-001 | Project Name : | INSURANCE AGENT PORTAL
Document Change History:
Ver.Rel. No | Release date | Modified By | Reviewed By | Approved By' | Modifications Done
1 | 2020-07-25 | Varun, Shreyash, Kartik | Simran | Jitesh | ILF, EIF, EI, EO, EQ, GSC, Effort Estimate Sheets Filled and Reviewed

## ILF
PM-02-01 Ver 1.0 /25-July-20 |  | Internal Logical Files
Internal Logical Files
ILF NAME | # of RETs | # of DETs | UFPs
Nav-bar | 1 | 6 | 7
Chat-Bot | 1 | 7 | 7
Footer | 1 | 5 | 7
Horizontal Slider on hone screen | 1 | 2 | 7
EMI Calculator | 1 | 3 | 7
Payment Details | 1 | 6 | 7
0
0
0
0
0
0
Total ILFs |  |  | 42
Note on B4: Enter appropriateInternal Logical File Name Internal Logical Files (ILF) - a user identifiable group of logically related data that resides entirely within the applications boundary and is maintained through External Inputs
Note on C4: Enter the no.of record Element Types Record Element Types is a user recognisable subgroup of data elements within an ILF or EIF. 2 types of subgroup Optional subgroup - Those that the user has the option of using one or none of the subgroups during an elementary process that adds or creates data mandatory subgroup - Those that the user must use at least one of the subgroups
Note on D4: Enter the no.of Data Element Types Data Element Types (DET) is a unique user recognisable, non recursive field on the ILF or EIF
Note on E4: The Unadjusted Function Points are calculated automatically by the formula provided

## EIF
| PM-02-01 Ver 1.0 /25-July-20 |  | External Interface Files
External Interface Files | External Interface Files
| EIF NAME | # of RETs | # of DETs | UFPs
| Appointment Details from Google Forms | 1 | 4 | 5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total EIFs |  |  | 5
Note on B4: L&T Infotech : Enter the appropriate name of External Interface File External Interface Files (EIF) - a user identifiable group of logically related data that is used for reference purposes only. The data resides entirely outside the application and is maintained by another application. The External Interface File is an Internal Logical File for another application.
Note on C4: Enter the no. of Record Element Types Record Element Types is a user recognisable subgroup of data elements within an ILF or EIF. 2 types of subgroup Optional subgroup - Those that the user has the option of using one or none of the subgroups during an elementary process that adds or creates data mandatory subgroup - Those that the user must use at least one of the subgroups
Note on D4: Enter the no. of Data Element Types Data Element Types (DET) is a unique user recognisable, non recursive field on the ILF or EIF
Note on E4: L&T Infotech : This calculates the no. of Unadjusted Function Points.
Note on B24: L&T Infotech : This calculates the total no. of External Interface files.

## EI
PM-02-01 Ver 1.0 /25-July-20 |  | External Inputs
External Inputs
EI NAME | # of FTRs | # of DETs | UFPs
APPOINTMENT DETAILS (ADD) | 1 | 6 | 3
EMI CALCULATOR (ADD) | 1 | 3 | 3
PAYMENT DETAILS (ADD) | 1 | 6 | 3
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total EIs |  |  | 9
Tips
* Do not forget to consider add, Modify and Delete as separate EIs
* Radio buttons are treated as DETs
* Check box represents one or more DETs
* Command button is treated as DET
* An image displayed is a DET. Ex. Item image in a catalogue
* Error messages and confirmation messages are treated as DETs
* A notification message (that involves getting input, rocessing with stored data and informing) is treated as EO
Note on B4: L&T Infotech : Enter the appropriate External Input name External Inputs (EI) - is an elementary process in which data crosses the boundary from outside to inside. This data may come from a data input screen, electronically or another application. The data can be either control information or business information. If the data is business information it is used to maintain one or more internal logical files. If the data is control information it does not have to update an internal logical file.
Note on C4: Enter the no. of File Types referenced - Internal Logical File read or maintained by a function type - External Interface type read by a function type
Note on D4: Enter the no. of Data Element Types Data Element Types (DET) is a unique user recognisable, non recursive field on the ILF or EIF
Note on E4: L&T Infotech : This automatically calculates the Unadjusted Function Points
Note on B23: L&T Infotech : This calculates the Total no. of External Inputs.

## EO
PM-02-01 Ver 1.0 /25-July-20 |  | External Outputs
External Outputs
EO NAME | # of FTRs | # of DETs | UFPs
0
Appointment Schedule | 1 | 6 | 4
Payment Reciept | 1 | 4 | 4
0
Total EOs |  |  | 8
Tips:Anotification message (that involves getting input,processing with stored data and informing) is treated as EO.
Note on B4: L&T Infotech : Enter the name of the External Output name External Outputs (EO) - an elementary process in which derived data passes across the boundary from inside to outside. The data creates reports or output files sent to other applications. These reports and files are created from one or more internal logical files and external interface file.
Note on C4: Enter the name of the FileTypes Referenced - Internal Logical File read or maintained by a function type - External Interface type read by a function type
Note on D4: Enter the no. of data Element Types Data Element Types (DET) is a unique user recognisable, non recursive field on the ILF or EIF
Note on E4: L&T Infotech : This automatically calculates the no.of unadjusted function points
Note on B9: L&T Infotech : This shows the total No. of External Outputs.

## EQ
PM-02-01 Ver 1.0 /25-July-20 |  |  |  | External Inquiry
External Inquiry
EQ NAME | Input |  | Output |  | UFPs | Input | Output
| # of FTRs | # of DETs | # of FTRs | # of DETs |  | FPs | FPs
Customer |  |  |  |  | 0 | 0 | 0 | 0
EMI Calculator | 1 | 3 | 3 | 1 | 3 | 3 | 3 | 3
Appointment Button | 1 | 1 | 1 | 4 | 3 | 3 | 3 | 3
Payment Details | 1 | 6 | 0 | 0 | 3 | 3 | 0 | 3
Agent |  |  |  |  | 0 | 0 | 0 | 0
Appointment Details |  |  | 1 | 4 | 3 | 0 | 3 | 3
Payment Details |  |  | 1 | 5 | 3 | 0 | 3 | 3
Total EQs |  |  |  |  | 15
Tips
* Picklists are queries from ILF or EIF, so they are counted as Eqs
* Dynamic Menus are considered Eqs (as the contents will be read from some file)
Note on B4: L&T Infotech : Enter the appropriate name of External query name External Inquiry (EQ) - is an elementary process with both input and output components that result in data retrieval from one or more internal logical files and external interface files. This information is sent outside the application boundary. The input process does not update any Internal Logical Files and the output side does not contain derived data.
Note on C4: LTITL: Enter the no of FTRs and DETs taking into account the input part.
Note on E4: LTITL: Enter the no of FTRs and DETs as far as Output is concerned.
Note on G4: L&T Infotech : This automatically calculates the Unadjusted FPs
Note on C5: L&T Infotech : Enter the no. of FTRs.
Note on D5: L&T Infotech : Enter no of DETs as inputs
Note on E5: L&T Infotech : Enter the no. of FTRs
Note on F5: L&T Infotech : Enter the no. of DETs.
Note on B13: L&T Infotech : This shows the Total no.of External Queries.

## Transformations
PM-02-01 Ver 1.0 / 25-July-20 |  | Transformations
Transformations
Transformation Name | Semantic Statement | Processing Steps | UFPs
0
0
0
Total |  |  | 0
Note: To be used only for Engineering or Embedded applications having complex algorithmic processing
Note on B3: For Comlex processing systems

## Transitions
PM-02-01 Ver 3.1 / 25-June-04 | Transitions
Transitions |  | Diagram of few complex modules are present.
Transitions | No of Transitions
Home Page | 12 | Refer: Word Document-Module Images
About Us Page | 11
Contact Us Page | 12
Payments Page | 17
Our Services Page | 11
Chat-Bot | 7
Total | 70
UFPs | 210
Note: To be used only for Engineering or Embedded applications having complex algorithmic processing
Note on B4: Transition occurs as a result of some event that causes the software to change its mode of behaviour
Note on C5: Header, Footer and EMI Calculator
Note on C6: Header, Footer
Note on C7: Header, Footer, Appointment Button
Note on C8: Header, Footer,Payment Details
Note on C9: Header, Footer

## GSC
PM-02-01 Ver 1.0 /25-July-20 |  | General System Characteristics
General System Characteristics
GSC | DI(0-5) | REMARKS
Data Communication | 3
Distributed Processing | 1
Performance | 1
Heavily Used Configuration | 0
Transaction Rates | 3
Online Data Entry | 5
End User Efficiency | 2
Online Update | 2
Complex Processing | 1 | Only Mathematical Processing for EMI Calculator
Reusability | 5
Installation Ease | 0
Operational Ease | 2
Multiple Site | 4
Facilitate Change | 0
Total Degree of Influence (TDI) | 29
VAF = 0.65 + (TDI x 0.01) | 0.94
Note on B4: LTITL: This column shows different types of General system Characteristics
Note on C4: 0 - No Influence 1 - Incidental Influence 2 - Moderate Influence 3 - Average Influence 4 - Significant Influence 5 - Strong Influence
Note on D4: LTITL: Put any remarks, if required.
Note on C5: Data Communications: 0 Application is pure batch processing or a standalone PC. 1 Application is batch but has remote data entry or remote printing. 2 Application is batch but has remote data entry and remote printing. 3 Application includes online data collection or TP (teleprocessing) front end to batch process or query system. 4 Application is more than a front-end, but supports only one type of TP communications protocol. 5 Application is more than a front-end and supports more than one type of TP communications protocol.
Note on C6: Distributed Data Processing: 0 Application does not aid the transfer of data or processing function between components of the system. 1 Application prepares data for end user processing on another component of the system such as PC spreadsheets and PC DBMS. 2 Data is prepared for transfer, then is transferred and processed on another component of the system (not for end-user processing). 3 Distributed processing and data transfer are online and in one direction only. 4 Distributed processing and data transfer are online and in both directions. 5 Processing functions are dynamically performed on the most appropriate component of the system
Note on C7: Performance: 0 No special performance requirements were stated by the user. 1 Performance and design requirements were stated and reviewed but no special actions were required. 2 Response time or throughput is critical during peak hours. No special design for CPU utilization was required. Processing deadline is for the next business day. 3 Response time or throughput is critical during all business hours. No special design for CPU utilization was required. Processing deadline requirements with interfacing systems are constraining. 4 In addition, stated user performance requirements are stringent enough to require performance analysis tasks in the design phase. 5 In addition, performance analysis tools were used in the design, development, and/or implementation phases to meet the stated user performance requirements
Note on C8: Heavily Used Configuration: 0 No explicit or implicit operational restrictions are included. 1 Operational restrictions do exist, but are less restrictive than a typical application. No special effort is needed to meet the restrictions. 2 Some security or timing considerations are included. 3 Specific processor requirements for a specific piece of the application are included. 4 Stated operation restrictions require special constraints on the application in the central processor or a dedicated processor. 5 In addition, there are special constraints on the application in the distributed components of the system.
Note on C9: Transaction Rate: 0 No peak transaction periodic anticipated 1 Peak transaction period (e.g., monthly, quarterly, seasonally, annually) is anticipated. 2 Weekly peak transaction period is anticipated. 3 Daily peak transaction period is anticipated. 4 High transaction rate(s) stated by the user in the application requirements or service level agreements are high enough to require performance analysis tasks in the design phase 5 High transaction rate(s) stated by the user in the application requirements or service level agreements are high enough to require performance analysis tasks and, in addition, require the use of performance analysis tools in the design, development, and/or installation phases.
Note on C10: Online Data Entry: 0 All transactions are processed in batch mode. 1 1% to 7% of transactions are interactive data entry. 2 8% to 15% of transactions are interactive data entry. 3 16% to 23% of transactions are interactive data entry. 4 24% to 30% of transactions are interactive data entry. 5 More than 30% of transactions are interactive data entry.
Note on C11: End-User Efficiency: ( Consider the following & use your Judgment)  Navigational aids (for example, function keys, jumps, dynamically generated menus)  Menus  Online help and documents.  List boxes, drop downs  Preassigned function keys  Heavy use of reverse video, highlighting, colours underlining, and other indicators.  Mouse and key board interface  As few screens as possible to accomplish a business function .  Ability to service untrained users.
Note on C12: Online Update: 0 None. 1 Online update of one to three control files is included. Volume of updating is low and recovery is easy. 2 Online update of four or more control files is included. Volume of updating is low and recovery easy. 3 Online update of major internal logical files is included. 4 In addition, protection against data lost is essential and has been specially designed and programmed in the system. 5 In addition, high volumes bring cost considerations into the recovery process. Highly automated recovery procedures with minimum operator intervention are included.
Note on C13: Complex Processing: ( Consider the following & use your Judgement)  Specific security processing.  Extensive logical processing  Extensive mathematical processing  Sensitive control (for example, special audit processing) and/or application  Much exception processing resulting in incomplete transactions that must be  Processed again, for example, incomplete ATM transactions caused by TP.  Interruption, missing data values, or failed edits
Note on C14: Reusability: 0 No reusable code 1 Reusable code is used within the application 2 Less than 10% of the application considered more than one user’s needs. 3 Ten percent (10%) or more of the application considered more than one user’s needs. 4 The application was specifically packaged and/or documented to ease re-use, and the application is customized by the user at source code level 5 The application was specifically packaged and/or documented to ease re-use, and the application is customized for use by means of user parameter maintenance.
Note on C15: Installation Ease: 0 No special considerations were stated by the user, and no special set-up is required for installation. 1 No special considerations were stated by the user but special set-up is required for installation. 2-3 Installation requirements were stated by the user, and installation guides were provided and tested. 4-5 In addition, automated installation tools were provided and tested.
Note on C16: Operational Ease: 0 No special operational considerations other than the normal back-up procedures were stated by the user 1-4 One , some, or all of the following items apply to the application. Effective start-up, back-up , and recovery processes were provided, but operator Intervention is required. Effective startup, back-up and recovery processes were Provided, but no operator intervention is required. The application minimizes. The need for tape mounts. 5 The application is designed for unattended operation. Unattended operation means no operator intervention is required to operate the system other than to start up or shut down the application. Automatic error recovery is a feature of the application.
Note on C17: Multiple Sites: 0 User requirements do not require considering the needs of more than one user/installation site. 1 Needs of multiple sites were considered in the design, and the application is designed to operate only under identical hardware and software environments 2 Needs of multiple sites were considered in the design, and the application is designed to operate only under similar hardware and/or software environments. 3 Needs of multiple sites were considered in the design, and the application is designed to operate only under different hardware and/or software environments. 4 Documentation and support plan are provided and tested to support the application at multiple sites and the application is as described by 1 or 2. 5 Documentation and support plan are provided and tested to support the application at multiple sites and the application is as described by 3.
Note on C18: Facilitate Change: ( Consider the following & use your Judgment)  Flexible query with query specification saving facility  Report layout customization  Screen customization  Ad-hoc report design

## FPA Summary for Development
PM-02-01 Ver 1.0 /25-July-20 | FPA Summary For Development
FPA Summery For Development
Function Point Count for | Unadjusted FPCs
ILF | 42
EIF | 5
EI | 9
EO | 16
EQ | 15
Transformations | 0
Transitions | 210
Total Unadjusted Function Points | 297
VAF | 0.94
Total Adjusted Function Points | 279.18
Note on B11: Not to be used for Business applications
Note on B12: Not to be used for Business applications

## Efforts estimate
PM-02-01 Ver 1.0 /25-July-20 |  |  |  |  | Effort Estimate
Total Effort Estimation
Size of the Project in FPs | 273
Factor to convert the size from FP to LOCs | 57
Productivity | 15
Efforts in Person Months | 47.1545
Requirement Stability Index | 100
Total Efforts in Person Months | 47.1545
Phasewise Distribution
| Phasewise distribution (%) | Efforts | Span Time | Resource Loading | Remarks
Total (PDLC) Efforts (by converting size) | 4 | 47.1545 | 0.15 | 314.3636
Requirements Analysis | 10 | 4.7155 | 0.3 | 15.7182
Design | 15 | 7.0732 | 0.45 | 15.7182
Coding | 34 | 16.0325 | 0.94 | 17.0559
Testing | 22 | 10.374 | 0.61 | 17.0066
Release & Implementation | 7 | 3.3008 | 0.26 | 12.6955
Other factors
Project management | 4 | 1.8862
QA | 2 | 0.94309
SCM, DP, training and other activities | 2 | 0.94309
Total Efforts for Other Factors in Person Months |  | 3.7724
Total Efforts in Person Months |  | 50.9269 | 2.56 | Total Span in Months
Note: * The phasewise distribution of % efforts has to be taken from the organizational goal It can be changed with proper justification for a project
Note on B5: This factor can be derived from the Caper Jones table given in the Caper Jones Table sheet It will be different for different languages. For Example for VB: One FP = 30 LOCs
Note on B6: Productivity in terms of Lines of code per day
Note on C6: Take the productivity for entire PDLC from Organizational Goal for the platform
Note on C8: RSI is an indicator available in the Organization Baseline. You may use RSI for calculating total efforts. This value is entered only for development projects.
Note on C12: Phasewise effort distribution is calculated based on the Phasewise distribution percentage
Note on D12: Phase wise Effort Distribution in Person Months
Note on E12: Span time in Months
Note on F12: No of resources required. The number is derived as Efforts in Person Months/ Span time in person Months
Note on G12: Enter the proper justification, if the Phasewise distribution percentage is different from Organization Goals.
Note on B14: Percentage efforts, calculated efforts , span time and resources required for the Requirements phase.
Note on B15: Percentage efforts, calculated efforts span time and resources required for the Design phase.
Note on B17: Percentage efforts, calculated efforts, span time and resources required for the Testing phase.
Note on B18: Percentage efforts, calculated efforts,span time and resources required for the Release & Implementation phase.
Note on C20: To be taken from Organization goals
Note on B21: Percentage efforts on Quality Assurance, efforts calculated for the project for QA activity, span time over which this activity is spread and resources required to execute the activity.
Note on C21: To be taken from Organization goals
Note on C22: Set on the basis of project requirement. Add the % of efforts required on SCM, Training, DP, Setup, etc..

## Assumptions and Risks
PM-02-01 Ver 3.1 /25-June-04 |  | Assumptions and Risks
Assumptions
Sr No | Assumptions
1 | User should at least have 2G net connection and a web browser
2 | No user manual required.
3 | Customer details will be taken through appointment details and payment details.
4 | In case of view operation, only the agent can view the payment appointment details the user cant.
Sr No | Risks

## Reference tables
PM-02-01 Ver 3.1 / 25-June-04 |  |  |  |  | Reference Tables
Quick Reference Tables for Various parameters
Internal Logical File Matrix |  |  |  |  | Complexity
|  | 1-19 DET | 20-50 DET | 51 + DETs | Complexity | UFP
| 1 RET | Low | Low | Avg | Low | 7
| 2 -5 RETs | Low | Avg | High | Average | 10
| 6+ RETs | Avg | High | High | High | 15
External Interface File Matrix |  |  |  |  | Complexity
|  | 1-19 DET | 20-50 DET | 51 + DETs | Complexity | UFP
| 1 RET | Low | Low | Avg | Low | 5
| 2 -5 RETs | Low | Avg | High | Average | 7
| 6+ RETs | Avg | High | High | High | 10
External Input Matrix |  |  |  |  | Complexity
|  | 1-4 DET | 5-15 DET | 16 + DETs | Complexity | UFP
| 0-1 FTRs | Low | Low | Avg | Very Low | 2
| 2 FTRs | Low | Avg | High | Low | 3
| 3+ FTRs | Avg | High | High | Average | 4
[5 empty] | High | 6
[5 empty] | Very High | 7
External Output Matrix |  |  |  |  | Complexity
|  | 1-5 DET | 6-19 DET | 20 + DETs | Complexity | UFP
| 0-1 FTRs | Low | Low | Avg | Very Low | 3
| 2 or 3FTRs | Low | Avg | High | Low | 4
| 3+ FTRs | Avg | High | High | Average | 5
[5 empty] | High | 7
[5 empty] | Very High | 9
External Inquiry Matrix |  |  |  |  | Complexity
| Input Part: | 1-4 DET | 5-15 DET | 16 + DETs | Complexity | UFP
| 0-1 FTRs | Low | Low | Avg | Very Low | 2
| 2 FTRs | Low | Avg | High | Low | 3
| 3+ FTRs | Avg | High | High | Average | 4
| Output Part: | 1-5 DET | 6-19 DET | 20 + DETs | High | 6
| 0-1 FTRs | Low | Low | Avg | Very High | 7
| 2 -3 FTRs | Low | Avg | High
| 4+ FTRs | Avg | High | High
Transformation Matrix |  |  |  |  | Complexity
Semantic Statements
| Processing Steps | 1-5 SS | 6-9 SS | 11+ SS | Complexity | UFP
| 1-10 PS | Low | Low | Avg | Very Low | 4
| 11-20 PS | Low | Avg | High | Low | 7
| 21+ PS | Avg | High | High | Average | 10
[5 empty] | High | 15
[5 empty] | Very High | 20

## Caper Jone table
PM-02-01 Ver 3.1 / 25-June-04 |  |  | Caper Jone Table
Productivity Conversion for Languages - FP to LOC |  |  | Productivity and Language Level
Note : The following table should be used in cases where Language level is not defined for a Particular technology in the above table. In such cases language level can be derived from the above table based on the similar technology. The derived language level can be input in the column provided in the table below (ItalicText) to readily calculate the Productivity in Function point.
Language | Level | Average LOCs per Function Point | Language Level | Average Productivity | Minimum of Language Level | Maximum of language level | Average Productivity (Min) | Average Productivity (Max) | Function Point / Language Level | Input Language Level | Productivity in FP / Person Month
1032/AF | 20 | 16 | 1 - 3 | 5 to 10 | 1 | 3 | 5 | 10 | 2.5 | 1 | 5
1st Generation default | 1 | 320 | 4 - 8 | 10 to 20 | 4 | 8 | 10 | 20 | 2.5 | 4 | 10
2nd Generation default | 3 | 107 | 9 - 16 | 16 to 23 | 9 | 16 | 16 | 23 | 1 | 9 | 16
3rd Generation default | 4 | 80 | 17 - 23 | 15 to 30 | 17 | 23 | 15 | 30 | 2.5 | 17 | 15
4th Generation default | 16 | 20 | 24 - 55 | 30 to 50 | 24 | 55 | 30 | 50 | 0.64516 | 24 | 30
5th Generation default | 70 | 5 | Above 55 | 40 to 100 | 56 | 100 | 40 | 100 | 1.3636 | 56 | 40
AAS Macro | 3.5 | 91
ABAP/4 | 20 | 16
ACCEL | 17 | 19
Access | 8.5 | 38
ACTOR | 15 | 21
Acumen | 11.5 | 28
Ada 83 | 4.5 | 71
Ada 95 | 6.5 | 49
ADR/DL | 8 | 40
ADR/IDEAL/PDL | 16 | 20
ADS/Batch | 16 | 20
ADS/Online | 16 | 20
AI shell default | 6.5 | 49
AI SHELLS | 6.5 | 49
ALGOL 68 | 3 | 107
ALGOL W | 3 | 107
AMBUSH | 10 | 32
AML | 6.5 | 49
AMPPL II | 5 | 64
ANSI BASIC | 5 | 64
ANSI COBOL 74 | 3 | 107
ANSI COBOL 85 | 3.5 | 91
ANSI SQL | 25 | 13
ANSWER/DB | 25 | 13
APL 360/370 | 10 | 32
APL default | 10 | 32
APL*PLUS | 10 | 32
APPLESOFT BASIC | 2.5 | 128
Application Builder | 16 | 20
Application Manager | 9 | 36
APS | 19 | 17
APT | 4.5 | 71
APTools | 16 | 20
ARC | 6.5 | 49
Ariel | 3 | 107
ARITY | 6.5 | 49
Arity PROLOG | 5 | 64
ART | 6.5 | 49
ART-IM | 7 | 46
ART Enterprise | 7 | 46
Artemis | 8 | 40
AS/SET | 17 | 19
ASI/INQUIRY | 25 | 13
ASK Windows | 7 | 46
Assembly (Basic) | 1 | 320
Assembly (Macro) | 1.5 | 213
Associative default | 5 | 64
Autocoder | 1 | 320
awk | 15 | 21
Aztec C | 2.5 | 128
BALM | 3 | 107
BASE SAS | 6 | 53
BASIC | 3 | 107
BASIC A | 2.5 | 128
Basic assembly | 1 | 320
Berkeley PASCAL | 3.5 | 91
BETTER BASIC | 3.5 | 91
BLISS | 3 | 107
BMSGEN | 9 | 36
BOEINGCALC | 50 | 6
BTEQ | 25 | 13
C | 2.5 | 128
C Set 2 | 3.5 | 91
C++ | 6 | 53
C86Plus | 2.5 | 128
CA-dBFast | 8 | 40
CA-EARL | 11.5 | 28
CAST | 6.5 | 49
CBASIC | 3.5 | 91
CDADL | 16 | 20
CELLSIM | 7 | 46
Centerline C++ | 6 | 53
CHILI | 3 | 107
CHILL | 3 | 107
CICS | 7 | 46
CLARION | 5.5 | 58
CLASCAL | 4 | 80
CLI | 10 | 32
CLIPPER | 17 | 19
CLIPPER DB | 8 | 40
CLOS | 15 | 21
CLOUT | 8 | 40
CMS2 | 3 | 107
CMSGEN | 17 | 19
COBOL | 3 | 107
COBOL II | 3 | 107
Cobol/400 | 3.5 | 91
COBRA | 16 | 20
CodeCenter | 9 | 36
Cofac | 9 | 36
COGEN | 9 | 36
COGNOS | 9 | 36
COGO | 4.5 | 71
COMAL | 4 | 80
COMIT II | 5 | 64
Common LISP | 5 | 64
Concurrent PASCAL | 4 | 80
CONNIVER | 5 | 64
CORAL 66 | 3 | 107
CORVET | 17 | 19
CorVision | 22 | 15
CPL | 2 | 160
Crystal Reports | 16 | 20
CSL | 6.5 | 49
CSP | 6 | 53
CSSL | 7 | 46
CULPRIT | 25 | 13
CxPERT | 6.5 | 49
CYGNET | 17 | 19
Data base default | 8 | 40
Dataflex | 8 | 40
Datatrieve | 16 | 20
dBase III | 8 | 40
dBase IV | 9 | 36
DCL | 1.5 | 213
DEC-RALLY | 8 | 40
Decision support default | 9 | 36
DELPHI | 11 | 29
DL/1 | 8 | 40
DNA-4 | 17 | 19
DOS Batch Files | 2.5 | 128
DSP Assembly | 2 | 160
DTABL | 7 | 46
DTIPT | 7 | 46
DYANA | 4.5 | 71
DYNAMO-III | 7 | 46
EASEL | 11 | 29
EASY | 6.5 | 49
EASYTRIEVE + | 25 | 13
Eclipse | 6.5 | 49
ED-Scheme 3.4 | 6 | 53
EDA/SQL | 27 | 12
EIFFEL | 15 | 21
ENFORM | 7 | 46
English-based default | 6 | 53
Ensemble | 11 | 29
EPOS | 16 | 20
Erlang | 8 | 40
ESF | 8 | 40
ESPADVISOR | 6.5 | 49
ESPL/I | 4.5 | 71
EUCLID | 3 | 107
EXCEL 1-2 | 51 | 6
EXCEL 3-4 | 55 | 6
EXCEL 5 | 57 | 6
EXPRESS | 9 | 36
EXSYS | 6.5 | 49
Extended Common LISP | 5.75 | 56
EZNOMAD | 9 | 36
Facets | 16 | 20
FactoryLink IV | 11 | 29
FAME | 9 | 36
FileMaker Pro | 9 | 36
FLAVORS | 11 | 29
FLEX | 7 | 46
FlexGen | 11 | 29
FOCUS | 8 | 40
FOIL | 6 | 53
Forte | 18 | 18
FORTH | 5 | 64
FORTRAN 66 | 2.5 | 128
FORTRAN 77 | 3 | 107
FORTRAN 90 | 4 | 80
FORTRAN 95 | 4.5 | 71
FORTRAN | 3 | 107
FORTRAN II | 2.5 | 128
Foundation | 11 | 29
FOXPRO 1 | 8 | 40
FOXPRO 2.5 | 9.5 | 34
FRAMEWORK | 50 | 6
G2 | 6.5 | 49
GAMMA | 20 | 16
Genascript | 12 | 27
GENER/OL | 25 | 13
GENEXUS | 21 | 15
GENIFER | 17 | 19
GeODE 2.0 | 20 | 16
GFA Basic | 9.5 | 34
GML | 7 | 46
Golden Common LISP | 5 | 64
GPSS | 7 | 46
GUEST | 11.5 | 28
Guru | 6.5 | 49
GW BASIC | 3.25 | 98
Haskell | 8.5 | 38
High C | 2.5 | 128
HLEVEL | 5.5 | 58
HP BASIC | 2.5 | 128
HTML 2.0 | 20 | 16
HTML 3.0 | 22 | 15
Huron | 20 | 16
IBM ADF I | 16 | 20
IBM ADF II | 18 | 18
IBM Advanced BASIC | 3.25 | 98
IBM CICS/VS | 8 | 40
IBM Compiled BASIC | 3.5 | 91
IBM VS COBOL | 3 | 107
IBM VS COBOL II | 3.5 | 91
ICES | 4.5 | 71
ICON | 4 | 80
IDMS | 8 | 40
IEF | 23 | 14
IEW | 23 | 14
IFPS/PLUS | 10 | 32
IMPRS | 8 | 40
INFORMIX | 8 | 40
INGRES | 8 | 40
INQUIRE | 25 | 13
INSIGHT2 | 6.5 | 49
INSTALL/1 | 20 | 16
INTELLECT | 6 | 53
INTERLISP | 5.5 | 58
Interpreted BASIC | 3 | 107
Interpreted C | 2.5 | 128
IQLISP | 5.5 | 58
IQRP | 25 | 13
JANUS | 4.5 | 71
JAVA | 6 | 53
JCL | 1.45 | 221
JOSS | 3 | 107
JOVIAL | 3 | 107
KAPPA | 8 | 40
KBMS | 6.5 | 49
KCL | 5 | 64
KEE | 6.5 | 49
Keyplus | 8 | 40
KL | 5 | 64
KLO | 5 | 64
KNOWOL | 6.5 | 49
KRL | 5.5 | 58
KSH | 15 | 21
Ladder Logic | 9 | 36
LAMBIT/L | 5 | 64
Lattice C | 2.5 | 128
Liana | 2.5 | 128
LILITH | 4.5 | 71
LINC II | 23 | 14
LISP | 5 | 64
LOGLISP | 5.5 | 58
LOOPS | 15 | 21
LOTUS 123 DOS | 50 | 6
LOTUS Macros | 3 | 107
LUCID 3D | 51 | 6
LYRIC | 6 | 53
M | 20 | 16
macFORTH | 5 | 64
MACH1 | 8 | 40
Machine language | 0.5 | 640
Macro assembly | 1.5 | 213
MAESTRO | 20 | 16
MAGEC | 20 | 16
MAGIK | 15 | 21
MAKE | 15 | 21
MANTIS | 8 | 40
MAPPER | 6 | 53
MARK IV | 8 | 40
MARK V | 9 | 36
MATHCAD | 60 | 5
MDL | 9 | 36
MENTOR | 6 | 53
MESA | 3 | 107
Microfocus COBOL | 4 | 80
microFORTH | 5 | 64
Microsoft C | 2.5 | 128
MicroStep | 16 | 20
Miranda | 8 | 40
Model 204 | 8.5 | 38
MODULA 2 | 4 | 80
MOSAIC | 50 | 6
MS C ++ V. 7 | 6 | 53
MS Compiled BASIC | 3.5 | 91
MSL | 5 | 64
muLISP | 5 | 64
MUMPS | 17 | 19
NASTRAN | 4.5 | 71
NATURAL 1 | 6 | 53
NATURAL 2 | 7 | 46
NATURAL Construct | 13 | 25
Natural language | 0.1 | 3200
NETRON/CAP | 17 | 19
NEXPERT | 6.5 | 49
NIAL | 6.5 | 49
NOMAD2 | 8 | 40
Non-procedural default | 9 | 36
Notes VIP | 9 | 36
Nroff | 6 | 53
Object-Oriented default | 11 | 29
OBJECT Assembler | 5 | 64
Object LISP | 11 | 29
Object LOGO | 11 | 29
Object PASCAL | 11 | 29
Object Star | 20 | 16
Objective-C | 12 | 27
ObjectVIEW | 13 | 25
OGL | 4 | 80
OMNIS 7 | 8 | 40
OODL | 11 | 29
OPS | 7 | 46
OPS5 | 5.5 | 58
ORACLE | 8 | 40
Oracle Developer/2000 | 14 | 23
Oscar | 3 | 107
PACBASE | 22 | 15
PACE | 8 | 40
PARADOX/PAL | 9 | 36
PASCAL | 3.5 | 91
PC FOCUS | 9 | 36
PDL Millenium | 15 | 21
PDP-11 ADE | 6 | 53
PERL | 15 | 21
Persistance Object Builder | 15 | 21
PILOT | 6 | 53
PL/I | 4 | 80
PL/M | 4.5 | 71
PL/S | 3.5 | 91
PLANIT | 6 | 53
PLANNER | 5 | 64
PLANPERFECT 1 | 45 | 7
PLATO | 6 | 53
polyFORTH | 5 | 64
POP | 5.5 | 58
POPLOG | 5.5 | 58
Power BASIC | 6.5 | 49
PowerBuilder | 20 | 16
POWERHOUSE | 23 | 14
PPL (Plus) | 8 | 40
Pro-C | 12 | 27
PRO-IV | 5.5 | 58
Problem-oriented default | 4.5 | 71
Procedural default | 3 | 107
Professional PASCAL | 3.5 | 91
Program Generator default | 20 | 16
PROGRESS V4 | 9 | 36
PROLOG | 5 | 64
PROSE | 3 | 107
PROTEUS | 3 | 107
QBasic | 5.5 | 58
QBE | 25 | 13
QMF | 22 | 15
QNIAL | 6.5 | 49
QUATTRO | 51 | 6
QUATTRO PRO | 51 | 6
Query default | 25 | 13
QUICK BASIC 1 | 5 | 64
QUICK BASIC 2 | 5.25 | 61
QUICK BASIC 3 | 5.5 | 58
Quick C | 2.5 | 128
Quickbuild | 11.5 | 28
QUIZ | 22 | 15
RALLY | 8 | 40
RAMIS II | 8 | 40
RapidGen | 11.5 | 28
RATFOR | 3.5 | 91
RDB | 8 | 40
REALIA | 7 | 46
Realizer 1.0 | 8 | 40
Realizer 2.0 | 9 | 36
RELATE/3000 | 8 | 40
Reuse default | 60 | 5
REXX (MVS) | 4 | 80
REXX (OS/2) | 7 | 46
RM BASIC | 3.5 | 91
RM COBOL | 3 | 107
RM FORTRAN | 3 | 107
RPG I | 4 | 80
RPG II | 5.5 | 58
RPG III | 5.75 | 56
RT-Expert 1.4 | 5.5 | 58
S-PLUS | 10 | 32
SAIL | 3 | 107
SAPIENS | 20 | 16
SAS | 10 | 32
SAVVY | 25 | 13
SBASIC | 3.5 | 91
SCEPTRE | 4.5 | 71
SCHEME | 6 | 53
Screen painter default | 57 | 6
SEQUAL | 27 | 12
SHELL | 15 | 21
SIMPLAN | 9 | 36
SIMSCRIPT | 7 | 46
SIMULA | 7 | 46
SIMULA 67 | 7 | 46
Simulation default | 7 | 46
SMALLTALK 286 | 15 | 21
SMALLTALK 80 | 15 | 21
SMALLTALK/V | 15 | 21
SNAP | 4 | 80
SNOBOL2-4 | 2.5 | 128
SoftScreen | 23 | 14
SOLO | 5.5 | 58
SPEAKEASY | 9 | 36
Spinnaker PPL | 9 | 36
Spreadsheet default | 50 | 6
SPS | 1 | 320
SPSS | 10 | 32
SQL | 25 | 13
SQL-Windows | 27 | 12
Statistical default | 10 | 32
STRATEGEM | 9 | 36
STRESS | 4.5 | 71
Strongly typed default | 3.5 | 91
STYLE | 7 | 46
SUPERBASE 1.3 | 9 | 36
SURPASS | 50 | 6
SYBASE | 8 | 40
Symantec C++ | 11 | 29
SYMBOLANG | 5 | 64
Synchroworks | 18 | 18
SYNON/2E | 17 | 19
System-W | 9 | 36
Tandem Access Language | 3.5 | 91
TCL | 5 | 64
TELON | 20 | 16
TESSARACT | 8 | 40
THE TWIN | 50 | 6
THEMIS | 25 | 13
TI-IEF | 23 | 14
Topspeed C ++ | 11 | 29
TRANSFORM | 22 | 15
TRANSLISP PLUS | 5.75 | 56
TREET | 5 | 64
TREETRAN | 5 | 64
TRS80 BASIC II,III | 2.5 | 128
TRUE BASIC | 5 | 64
Turbo C | 2.5 | 128
TURBO C++ | 6 | 53
TURBO EXPERT | 6.5 | 49
Turbo PASCAL >5 | 6.5 | 49
Turbo PASCAL 1-4 | 4 | 80
Turbo PASCAL 4-5 | 4.5 | 71
Turbo PROLOG | 4 | 80
TURING | 4 | 80
TUTOR | 6 | 53
TWAICE | 6.5 | 49
UCSD PASCAL | 3.5 | 91
UFO/IMS | 9 | 36
UHELP | 10 | 32
UNIFACE | 20 | 16
UNIX Shell Scripts | 15 | 21
VAX ACMS | 5.5 | 58
VAX ADE | 8 | 40
VECTRAN | 3 | 107
VHDL | 17 | 19
Visible C | 6.5 | 49
Visible COBOL | 8 | 40
Visicalc 1 | 35 | 9
Visual 4.0 | 11 | 29
Visual Basic 1 | 7 | 46
Visual Basic 2 | 7.5 | 43
Visual Basic 3 | 8 | 40
Visual Basic 4 | 9 | 36
Visual Basic 5 | 11 | 29
Visual Basic DOS | 8 | 40
Visual C++ | 9.5 | 34
Visual COBOL | 16 | 20
Visual Objects | 20 | 16
VisualAge | 15 | 21
VisualGen | 18 | 18
VS-REXX | 10 | 32
VULCAN | 5 | 64
VZ Programmer | 9 | 36
WARP X | 8 | 40
WATCOM C | 2.5 | 128
WATCOM C/386 | 2.5 | 128
Waterloo C | 2.5 | 128
Waterloo PASCAL | 3.5 | 91
WATFIV | 3.75 | 85
WATFOR | 3.5 | 91
WHIP | 3.5 | 91
Wizard | 11.5 | 28
XLISP | 5 | 64
YACC | 6 | 53
YACC++ | 6 | 53
ZBASIC | 3.5 | 91
ZIM | 17 | 19
ZLISP | 5 | 64
Note on G7: Average Productivity per PersonMonth in Function Points
Note on J7: Minimum Average Productivity per PersonMonth in Function Points
Note on K7: Maximum Average Productivity per PersonMonth in Function Points
Note on M7: Please Input Language level (Default is Minimum of the range)
Note on I13: Assumed Value : To be decided by Individual Project Team.