## WAS
PM-01-02 Ver 2.01 / 29-Sep-04 |  |  | Work Allocation Sheet
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Sr. No. | PDLC Stage | Module Name | Work Item / Review Item | Type | Assigned To | Reference file ID / Bug ID | Planned Time in Hours | Planned Start Date | Planned End Date | Actual Time in Hours | Actual Start Date | Actual End Date | Planned Effort (Hrs) | Actual Effort (Hrs) | Number of Resources | Status | Dependencies | Remarks
1 | Requirement | Requirements Checklists | Filling Checklists | core work | TM | P-RC | 114 | 2020-07-13 | 2020-07-26 | 114 | 2020-07-13 | 2020-07-23 | 280 | 114 | 6 | Completed | Project Acceptance
2 | Requirement | Requirements Checklists | Review | Review | PL | P-RC |  | 2020-07-14 | 2020-07-27 |  | 2020-07-14 | 2020-07-24 |  |  |  | Completed
3 | Requirement | Documentation of requirements | Documentation | core work | TM | P-DR |  | 2020-07-15 | 2020-07-28 |  | 2020-07-15 | 2020-07-25 |  |  |  | Completed
4 | Requirement | Documentation of requirements | Review | Review | PL | P-DR |  | 2020-07-16 | 2020-07-30 |  | 2020-07-16 | 2020-07-30 |  |  |  | Completed
Estimation Phase
5 | Estimation | Estimation using Function Point Analysis | Filling Documents | core work | TM | P-FP | 50 | 2020-07-30 | 2020-08-06 | 25 | 2020-07-30 | 2020-08-06 | 50 | 25 | 6 | Completed | Requirement Documentation
6 | Estimation | Estimation using Function Point Analysis | Review | Review | PL | P-FP |  | 2020-07-30 | 2020-08-06 |  | 2020-07-30 | 2020-08-06 |  |  |  | Completed
7 | Estimation | Estimation using PCM | Filling Documents | core work | TM | P-PM |  | 2020-07-30 | 2020-08-06 |  | 2020-07-30 | 2020-08-06 |  |  |  | Completed
8 | Estimation | Estimation using PCM | Review | Review | PL | P-PM |  | 2020-07-30 | 2020-08-06 |  | 2020-07-30 | 2020-08-06 |  |  |  | Completed
9 | Estimation | Estimation using BS | Filling Documents | core work | TM | P-BS |  | 2020-07-30 | 2020-08-06 |  | 2020-07-30 | 2020-08-06 |  |  |  | Completed
10 | Estimation | Estimation using BS | Review | Review | PL | P-BS |  | 2020-07-30 | 2020-08-06 |  | 2020-07-30 | 2020-08-06 |  |  |  | Completed
Design Phase
HLD
13 | Design | Design-HLD using SSAD | HLD | Core work | TM | P-LD |  | 2020-08-10 | 2020-08-16 |  | 2020-08-24 | 2020-09-20 | 424 | 83.6 | 8 | Completed | Requirement and Estimation Documentation
13.1.1 | Design | Determination of Development Enviornment | Documentation | Core work | Shreyash A. | P-LD-1 | 1 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.1.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-10 | 2020-08-16 | 2 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.2.1 | Design | Determination of Modular Specification | Documentation | Core work | Varun K. | P-LD-2 | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.2.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 2 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.3.1 | Design | Determination of Design Approach | Documentation | Core work | Jitesh M. | P-LD-3 | 1 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.3.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1.5 | 2020-08-10 | 2020-08-16 | 2 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.4.1 | Design | Determination of System Architecture | Documentation | Core work | Simran K. | P-LD-4 | 3 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.4.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 1.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.5.1 | Design | Designing HLD | Documentation | Core work | Kartik P. | P-LD-5 | 2.5 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.5.2 | Design | Knowledge Gathering of the Respective Topic |  | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
14 | Design | Design-HLD | Review | Review | PL(Jitesh M.) | P-LD-R | 1 | 2020-08-10 | 2020-08-16 | 0.6 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
DLD
15 | Design | Design-DLD using SSAD | DLD | Core work | TM | P-HD |  | 2020-08-17 | 2020-08-23 |  | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.1 | Design | Design-DLD using SSAD for Section 1 | Documentation | Core work | Shreyash A. | P-HD-1 | 2 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 4 | 2020-08-17 | 2020-08-23 | 4 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.3 | Design | Design-DLD using SSAD for Section 2 | Documentation | Core work | Shreyash A. | P-HD-1 | 2.5 | 2020-08-17 | 2020-08-23 | 3.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.4 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 3.5 | 2020-08-17 | 2020-08-23 | 6.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.1 | Design | Design-DLD using SSAD for Section 3 | Documentation | Core work | Varun K. | P-HD-2 | 2.7 | 2020-08-17 | 2020-08-23 | 3.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 3.5 | 2020-08-17 | 2020-08-23 | 6.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.3 | Design | Design-DLD using SSAD for Section 4 | Documentation | Core work | Varun K. | P-HD-2 | 2 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.4 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 3 | 2020-08-17 | 2020-08-23 | 4 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
PS
15.3.1 | Design | Documentation of Client Server Enviornment Section 1 | Documentation | Core work | Jitesh M. | P-HD-3 | 2 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.3.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 3.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.3.3 | Design | Documentation of Client Server Enviornment Section 2 | Documentation | Core work | Jitesh M. | P-HD-3 | 2 | 2020-08-17 | 2020-08-23 | 3 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.3.4 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2.5 | 2020-08-17 | 2020-08-23 | 4.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.1 | Design | Documentation of Client Server Enviornment Section 3 | Documentation | Core work | Simran K. | P-HD-4 | 2 | 2020-08-17 | 2020-08-23 | 3 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 4.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.3 | Design | Documentation of Client Server Enviornment Section 4 | Documentation | Core work | Simran K. | P-HD-4 | 1 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.4 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 3 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.1 | Design | Determination of Client Server Enviornment Section 5 | Documentation | Core work | Kartik P. | P-HD-5 | 1.5 | 2020-08-17 | 2020-08-23 | 1.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.3 | Design | Determination of Client Server Enviornment Section 6 | Documentation | Core work | Kartik P. | P-HD-5 | 1 | 2020-08-17 | 2020-08-23 | 1 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.4 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1.5 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
16 | Design | Design-HLD | Review | Review | PL(Jitesh M.) | P-HD-R | 1.5 | 2020-08-17 | 2020-08-23 | 2 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
Development Phase
17 | Development | Home Page | Coding | Core work | TM | P-HP |  | 2020-08-17 | 2020-08-23 |  |  |  | 952 |  | 10 | Planned | Requirement, Design and Estimation Documentation
18 | Development | Home Page | Review | Review | PL | P-HP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
19 | Development | About Us | Coding | Core work | TM | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
20 | Development | About Us | Review | Review | PL | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
21 | Development | Our Services | Coding | Core work | TM | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
22 | Development | Our Services | Review | Review | PL | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
23 | Development | Payments | Coding | Core work | TM | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
24 | Development | Payments | Review | Review | PL | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
25 | Development | Contact Us | Coding | Core work | TM | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
26 | Development | Contact Us | Review | Review | PL | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
27 | Development | Chat-Bot | Coding | Core work | TM | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
28 | Development | Chat-Bot | Review | Review | PL | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
29 | Development | Nav-Bar | Coding | Core work | TM | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
30 | Development | Nav-Bar | Review | Review | PL | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
31 | Development | Footer | Coding | Core work | TM | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
32 | Development | Footer | Review | Review | PL | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
33 | Development | Database Management of G-Forms input | Coding | Core work | TM | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
34 | Development | Database Management of G-Forms input | Review | Review | PL | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
35 | Development | Database Management Of Payment Details | Coding | Core work | TM | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
36 | Development | Database Management Of Payment Details | Review | Review | PL | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
37 | Development | Miscellaneous Database Management | Coding | Core work | TM | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
38 | Development | Miscellaneous Database Management | Review | Review | PL | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
Testing Phase
39 | Testing | Unit Testing of Slideshow | Unit Testing | Core work | TM | P-HP | 3 | 2020-08-24 | 2020-08-30 | 3 | 2020-09-14 | 2020-09-20 | 616 | 32.5 | 11 | Completed | Requirement, Design and Estimation Documentation with Developed Software
40 | Testing | Unit Testing of Slideshow | Review | Review | PL | P-HP | 2 | 2020-08-24 | 2020-08-30 | 2.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
41 | Testing | Unit Testing in Our Services | Unit Testing | Core work | TM | P-AU | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
42 | Testing | Unit Testing in Our Services | Review | Review | PL | P-AU | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
43 | Testing | Unit Testing of Our Vision | Unit Testing | Core work | TM | P-OS | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
44 | Testing | Unit Testing of Our Vision | Review | Review | PL | P-OS | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
45 | Testing | Unit Testing of EMI Calculator | Unit Testing | Core work | TM | P-PS | 3 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
46 | Testing | Unit Testing of EMI Calculator | Review | Review | PL | P-PS | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
47 | Testing | Unit Testing of News Section | Unit Testing | Core work | TM | P-CU | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
48 | Testing | Unit Testing of News Section | Review | Review | PL | P-CU | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
49 | Testing | Testing of Integrated Modules | Integration testing | Core work | TM | P-IM-IT | 4 | 2020-08-24 | 2020-08-30 | 4 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
50 | Testing | Testing of Integrated Modules | Review | Review | PL | P-IM-IT | 2 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
51 | Testing | System Testing of Integerated Modules | System Testing | Core work | TM | P-IM-ST | 3 | 2020-08-24 | 2020-08-30 | 3 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
52 | Testing | System Testing of Integerated Modules | Review | Review | PL | P-IM-ST | 1 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
Deployment Phase
55 | Deployment | Integerated Modules | Publishing site and setting up the database. | Core work | TM | P-IM-PL |  | 2020-08-31 | 2020-09-06 |  |  |  | 192 |  | 8 | Planned | Requirement, Design and Estimation Documentation with Developed Software
56 | Deployment | Integerated Modules | Review | Review | PL | P-IM-PL |  | 2020-08-31 | 2020-09-06 | [6 empty] | Planned
Maintainance Phase
57 | Maintainance | Integerated Modules | Maintainace of the site | Core work | TM | P-IM-MC |  | 2020-09-06 | 2020-12-05 |  |  |  | To be estimated later |  | 10 | Planned | Requirement, Design and Estimation Documentation and Developed Software
58 | Maintainance | Integerated Modules | Review | Review | PL | P-IM-MC |  | 2020-09-06 | 2020-12-05 | [6 empty] | Planned