## WAS
PM-01-02 Ver 2.01 / 29-Sep-04 |  |  | Work Allocation Sheet
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Sr. No. | PDLC Stage | Module Name | Work Item / Review Item | Type | Assigned To | Reference file ID / Bug ID | Planned Time in Hours | Planned Start Date | Planned End Date | Actual Time in Hours | Actual Start Date | Actual End Date | Planned Effort (Hrs) | Actual Effort (Hrs) | Number of Resources | Status | Dependencies | Remarks
1 | Requirement | Requirements Checklists | Filling Checklists | core work | TM | P-RC | 136 | 2020-07-13 | 2020-07-26 | 149.7 | 2020-07-13 | 2020-07-23 | 223 | 200 | 6 | Completed | Project Acceptance
2 | Requirement | Requirements Checklists | Review | Review | PL | P-RC |  | 2020-07-14 | 2020-07-27 |  | 2020-07-14 | 2020-07-24 |  |  |  | Completed
3 | Requirement | Documentation of requirements | Documentation | core work | TM | P-DR |  | 2020-07-15 | 2020-07-28 |  | 2020-07-15 | 2020-07-25 |  |  |  | Completed
4 | Requirement | Documentation of requirements | Review | Review | PL | P-DR |  | 2020-07-16 | 2020-07-29 |  | 2020-07-16 | 2020-07-26 |  |  |  | Completed
Estimation Phase
5 | Estimation | Estimation using Function Point Analysis | Filling Documents | core work | TM | P-FP | - | 2020-07-26 | 2020-08-01 | - | 2020-07-24 | 2020-07-28 | 130 | 120 | 6 | Completed | Requirement Documentation
6 | Estimation | Estimation using Function Point Analysis | Review | Review | PL | P-FP | - | 2020-07-27 | 2020-08-02 | - | 2020-07-25 | 2020-07-29 |  |  |  | Completed
7 | Estimation | Estimation using PCM | Filling Documents | core work | TM | P-PM | - | 2020-07-28 | 2020-08-03 | - | 2020-07-26 | 2020-07-30 |  |  |  | Completed
8 | Estimation | Estimation using PCM | Review | Review | PL | P-PM | - | 2020-07-29 | 2020-08-04 | - | 2020-07-27 | 2020-07-31 |  |  |  | Completed
9 | Estimation | Estimation using BS | Filling Documents | core work | TM | P-BS | - | 2020-07-30 | 2020-08-05 | - | 2020-07-28 | 2020-08-01 |  |  |  | Completed
10 | Estimation | Estimation using BS | Review | Review | PL | P-BS | - | 2020-07-31 | 2020-08-06 | - | 2020-07-29 | 2020-08-02 |  |  |  | Completed
Design Phase
13 | Design | Design-HLD using SSAD | HLD | Core work | TM | P-LD |  | 2020-08-10 | 2020-08-16 |  | 2020-08-24 | 2020-09-20 | 16.23 | 23.5 | 8 | Completed | Requirement and Estimation Documentation
13.1.1 | Design | Determination of Development Enviornment | Documentation | Core work | Shreyash A. | P-LD-1 | 0.8 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.1.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.2.1 | Design | Determination of Modular Specification | Documentation | Core work | Varun K. | P-LD-2 | 0.5 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.2.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.3.1 | Design | Determination of Design Approach | Documentation | Core work | Jitesh M. | P-LD-3 | 1 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.3.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1.5 | 2020-08-10 | 2020-08-16 | 1 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.4.1 | Design | Determination of System Architecture | Documentation | Core work | Simran K. | P-LD-4 | 2 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.4.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 1.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.5.1 | Design | Designing HLD | Documentation | Core work | Kartik P. | P-LD-5 | 2.5 | 2020-08-10 | 2020-08-16 | 3 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
13.5.2 | Design | Knowledge Gathering of the Respective Topic |  | Core work |  |  | 1 | 2020-08-10 | 2020-08-16 | 1.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
14 | Design | Design-HLD | Review | Review | PL(Jitesh M.) | P-LD-R | 0.5 | 2020-08-10 | 2020-08-16 | 0.5 | 2020-08-24 | 2020-09-20 |  |  |  | Completed
15 | Design | Design-DLD using SSAD | DLD | Core work | TM | P-HD |  | 2020-08-17 | 2020-08-23 |  | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.1 | Design | Design-DLD using SSAD | Documentation | Core work | Shreyash A. | P-HD-1 | 1 | 2020-08-17 | 2020-08-23 | 0.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.1.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 0.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.1 | Design | Design-DLD using SSAD | Documentation | Core work | Varun K. | P-HD-2 | 1 | 2020-08-17 | 2020-08-23 | 0.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.2.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 1 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.3.1 | Design | Determination of Client Server Enviornment | Documentation | Core work | Jitesh M. | P-HD-3 | 3 | 2020-08-17 | 2020-08-23 | 0.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.3.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 1.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.1 | Design | Design-DLD using SSAD | Documentation | Core work | Simran K. | P-HD-4 | 1 | 2020-08-17 | 2020-08-23 | 1 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.4.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 1 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.1 | Design | Determination of Client Server Enviornment | Documentation | Core work | Kartik P. | P-HD-5 | 3 | 2020-08-17 | 2020-08-23 | 1.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
15.5.2 | Design | Knowledge Gathering of the Respective Topic | Knowledge Gathering | Core work |  |  | 2 | 2020-08-17 | 2020-08-23 | 1 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
16 | Design | Design-HLD | Review | Review | PL(Jitesh M.) | P-HD-R | 1 | 2020-08-17 | 2020-08-23 | 0.5 | 2020-08-31 | 2020-09-20 |  |  |  | Completed
Development Phase
17 | Development | Home Page | Coding | Core work | TM | P-HP |  | 2020-08-17 | 2020-08-23 |  |  |  | 699 |  | 10 | Planned | Requirement, Design and Estimation Documentation
18 | Development | Home Page | Review | Review | PL | P-HP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
19 | Development | About Us | Coding | Core work | TM | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
20 | Development | About Us | Review | Review | PL | P-AU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
21 | Development | Our Services | Coding | Core work | TM | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
22 | Development | Our Services | Review | Review | PL | P-OS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
23 | Development | Payments | Coding | Core work | TM | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
24 | Development | Payments | Review | Review | PL | P-PS |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
25 | Development | Contact Us | Coding | Core work | TM | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
26 | Development | Contact Us | Review | Review | PL | P-CU |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
27 | Development | Chat-Bot | Coding | Core work | TM | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
28 | Development | Chat-Bot | Review | Review | PL | P-CB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
29 | Development | Nav-Bar | Coding | Core work | TM | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
30 | Development | Nav-Bar | Review | Review | PL | P-NB |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
31 | Development | Footer | Coding | Core work | TM | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
32 | Development | Footer | Review | Review | PL | P-FT |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
33 | Development | Database Management of G-Forms input | Coding | Core work | TM | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
34 | Development | Database Management of G-Forms input | Review | Review | PL | P-DG |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
35 | Development | Database Management Of Payment Details | Coding | Core work | TM | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
36 | Development | Database Management Of Payment Details | Review | Review | PL | P-DP |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
37 | Development | Miscellaneous Database Management | Coding | Core work | TM | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
38 | Development | Miscellaneous Database Management | Review | Review | PL | P-MM |  | 2020-08-17 | 2020-08-23 | [6 empty] | Planned
Testing Phase
39 | Testing | Unit Testing of Slideshow | Unit Testing | Core work | TM | P-HP | 1 | 2020-08-24 | 2020-08-30 | 1 | 2020-09-14 | 2020-09-20 | 460 | 12 | 11 | Completed | Requirement, Design and Estimation Documentation with Developed Software
40 | Testing | Unit Testing of Slideshow | Review | Review | PL | P-HP | 1 | 2020-08-24 | 2020-08-30 | 1 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
41 | Testing | Unit Testing in Our Services | Unit Testing | Core work | TM | P-AU | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
42 | Testing | Unit Testing in Our Services | Review | Review | PL | P-AU | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
43 | Testing | Unit Testing of Our Vision | Unit Testing | Core work | TM | P-OS | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
44 | Testing | Unit Testing of Our Vision | Review | Review | PL | P-OS | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
45 | Testing | Unit Testing of EMI Calculator | Unit Testing | Core work | TM | P-PS | 2 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
46 | Testing | Unit Testing of EMI Calculator | Review | Review | PL | P-PS | 2 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
47 | Testing | Unit Testing of News Section | Unit Testing | Core work | TM | P-CU | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
48 | Testing | Unit Testing of News Section | Review | Review | PL | P-CU | 1 | 2020-08-24 | 2020-08-30 | 0.5 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
49 | Testing | Testing of Integrated Modules | Integration testing | Core work | TM | P-IM-IT | 3 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
50 | Testing | Testing of Integrated Modules | Review | Review | PL | P-IM-IT | 2 | 2020-08-24 | 2020-08-30 | 1 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
51 | Testing | System Testing of Integerated Modules | System Testing | Core work | TM | P-IM-ST | 3 | 2020-08-24 | 2020-08-30 | 2 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
52 | Testing | System Testing of Integerated Modules | Review | Review | PL | P-IM-ST | 2 | 2020-08-24 | 2020-08-30 | 1 | 2020-09-14 | 2020-09-20 |  |  |  | Completed
Deployment Phase
55 | Deployment | Integerated Modules | Publishing site and setting up the database. | Core work | TM | P-IM-PL |  | 2020-08-31 | 2020-09-06 |  |  |  | 195 |  | 8 | Planned | Requirement, Design and Estimation Documentation with Developed Software
56 | Deployment | Integerated Modules | Review | Review | PL | P-IM-PL |  | 2020-08-31 | 2020-09-06 | [6 empty] | Planned
Maintainance Phase
57 | Maintainance | Integerated Modules | Maintainace of the site | Core work | TM | P-IM-MC |  | 2020-09-06 | 2020-12-05 |  |  |  | To be estimated later |  | 10 | Planned | Requirement, Design and Estimation Documentation and Developed Software
58 | Maintainance | Integerated Modules | Review | Review | PL | P-IM-MC |  | 2020-09-06 | 2020-12-05 | [6 empty] | Planned
Note on B6: ====== ID#AAAAGyBZEtA Administrator (2020-08-04 07:06:38) Running serial Number
Note on C6: ====== ID#AAAAGyBZEtI SSS (2020-08-04 07:06:38) PDLC Stage Name e.g. Requirement, Design, Coding, Testing, etc.
Note on D6: ====== ID#AAAAGyBZEtc SSS (2020-08-04 07:06:38) Module Name
Note on E6: ====== ID#AAAAGyBZEtU SSS (2020-08-04 07:06:38) Individual Work Item / Review item for the PDLC Stage and Module. E.g. Report Design, Screen Design, Function to be coded
Note on F6: ====== ID#AAAAGyBZEts Sundar (2020-08-04 07:06:38) Work allocation Review Rework Re-review
Note on G6: ====== ID#AAAAGyBZEtM SSS (2020-08-04 07:06:38) PL, Team Member to whom the work / review item is assigned
Note on H6: ====== ID#AAAAGyBZEtE Sundar (2020-08-04 07:06:38) Reference file ID / Bug ID for Review, Rework, Re-review
Note on J6: ====== ID#AAAAGyBZEuA SSS (2020-08-04 07:06:38) Planned start date for the work item
Note on K6: ====== ID#AAAAGyBZEtY SSS (2020-08-04 07:06:38) Planned end date for the Work Item
Note on M6: ====== ID#AAAAGyBZEt8 SSS (2020-08-04 07:06:38) Actual Start date
Note on N6: ====== ID#AAAAGyBZEtw SSS (2020-08-04 07:06:38) Actual end date for the work item
Note on O6: ====== ID#AAAAGyBZEt4 SSS (2020-08-04 07:06:38) Planned Effort for the work item in Hrs
Note on P6: ====== ID#AAAAGyBZEt0 SSS (2020-08-04 07:06:38) Actual Effort for the work item in Hrs
Note on Q6: ====== ID#AAAAGyBZEtk ISD (2020-08-04 07:06:38) Number of resources allocated for the work item
Note on R6: ====== ID#AAAAGyBZEtg SSS (2020-08-04 07:06:38) Planned, Started, Completed, Postponed, Cancelled, Transferred (when the work item is transferred from one resource to another. In this case retain the first allocation entry with Transferred status with Actual End Date showing transfer date. Add new entry for showing new resource name and new planned date.
Note on S6: ====== ID#AAAAGyBZEto skk-prj (2020-08-04 07:06:38) Mention the serial nos. Of work items whose completion is prerequisite for this work item.
Note on T6: ====== ID#AAAAGyBZEtQ Administrator (2020-08-04 07:06:38) Explanatory Text, if required, for the entry
Note on Q8: ====== ID#AAAAKEIE6-Q jitesh mishra (2020-08-06 06:28:32) 5 team members, Project Acceptance Documentation.
Note on Q13: ====== ID#AAAAKEIE6-Y jitesh mishra (2020-08-06 06:29:54) 5 team members,Requirement Documentation.
Note on Q20: ====== ID#AAAAKJy46xs jitesh mishra (2020-08-27 04:41:32) 5 Team Members, Requirement Document,UML Software, Estimation Documentation
Note on Q45: ====== ID#AAAAKEIE7NI jitesh mishra (2020-08-06 07:22:01) 5 Team Members, Requirement Documentation, Estimation Documentation, Angular 10,Visual Studio Code, Git-Hub.
Note on Q68: ====== ID#AAAAKEIE7Ng jitesh mishra (2020-08-06 07:24:23) 5 Team Members, Requirement Documentation, Estimation Documentation, Angular 10,Google Insights, Git-Hub and server
Note on Q83: ====== ID#AAAAKEIE7PU jitesh mishra (2020-08-06 07:28:15) 5 Team Members, Requirement Documentation, Estimation Documentation and Server.
Note on Q86: ====== ID#AAAAKEIE7Po jitesh mishra (2020-08-06 07:31:49) 5 Team Members, Requirement Documentation, Angular 10,Visual Studio Code, Git-Hub, Google Insights.