## ChangeHistory
PM-02-02 Ver 1.0 / 26-July-20 |  |  |  | Change History
Project ID: |  | IAP-001 | Project Name : | INSURANCE AGENT PORTAL
Document Change History:
Ver.Rel. No | Release date | Modified By | Reviewed By | Approved By' | Modifications Done
1 | 2020-07-26 | Kartik, Varun, Shreyash | Simran Kumari | Jitesh Mishra | Work Breakdown, PCM Estimation Summary Assumptions, Efforts Estimate Sheets Filled and Reviewed.
Note :Since the estimation is baseline item. We need to keep history of changes. This sheet should be used to keep track of the changes.

## Work Breakdown
PM-02-02 Ver 1.0 / 26-July-20 |  | Work Breakdown
Home Page |  |  |  | Diagram of few complex modules are present.
Program Name | Simple | Medium | Complex
Horizantal Slider |  |  | 1 | Refer: Word Document-Module Images
Our Services Section | 1
Our Vision Section | 1
EMI Calculator |  |  | 1
News Section | 1
Total for Home Page | 3 | 0 | 2
About Us
Program Name | Simple | Medium | Complex
Text Description of Agent | 1
Total for About Us | 1 | 0 | 0
Payments
Program Name | Simple | Medium | Complex
Input Field to Enter Customer Data | 1
Text Area to Give Agent's Bank Details | 1
Submit Button to Submit the Details |  |  | 1
Total for Payments | 2 | 0 | 1
Contact Us
Program Name | Simple | Medium | Complex
Text Area to Give Agent's Contact Details | 1
Button Leading to Google Forms |  | 1
Total for Contact Us | 1 | 1 | 0
Our Services
Program Name | Simple | Medium | Complex
Text Description of Services | 1
Image Complementing to the text | 1
Total for Our Services | 2 | 0 | 0
Chat-Bot
Program Name | Simple | Medium | Complex
Button To Open and Close Chat-Bot |  |  | 1
5 Navigation Links |  | 1
Textbox to Enter Queries |  |  | 1
Total for Chat-Bot | 0 | 1 | 2
Nav-Bar
Program Name | Simple | Medium | Complex
5 Navigation Text Links |  | 1
1 Navigation Symbol Links |  | 1
Total for Nav-Bar | 0 | 2 | 0
Footer
Program Name | Simple | Medium | Complex
5 Navigation Text Links |  | 1
Total for Footer | 0 | 1 | 0
Server Side Communication
Program Name | Simple | Medium | Complex
Communication between database and google forms |  |  | 1
Communication between database and website |  |  | 1
Total for Chat-Bot | 0 | 0 | 2
DBMS
Program Name | Simple | Medium | Complex
Payment Details Database Template |  |  | 1
Appointment Details Database Template |  |  | 1
E2 Database Template |  |  | 1
Total for Chat-Bot | 0 | 0 | 3
Note on C5: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D5: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E5: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C17: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D17: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E17: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C29: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D29: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E29: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C39: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D39: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E39: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C49: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D49: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E49: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C61: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D61: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E61: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C73: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D73: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E73: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C85: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D85: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E85: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C97: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D97: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E97: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.
Note on C109: Write the definition of Simple program in the assumption sheet. Enter 1 if the program is simple.
Note on D109: Write the definition of Medium program in the assumption sheet. Enter 1 if the program is Medium.
Note on E109: Write the definition of complex program in the assumption sheet. Enter 1 if the program is complex.

## Efforts estimate
PM-02-02 Ver 1.0 / 26-July-20 |  |  |  |  | Effort Estimate
Total Effort Estimation
Function Complexity | Simple | Medium | Complex
No of Functions in the Category | 9 | 5 | 10
Productivity per function in Person days | 0.25 | 1.5 | 2
Efforts in Person days | 2.25 | 7.5 | 20
Total Coding Efforts (Person months) | 1.3523
Effort distribution for coding in % | 70
Total efforts (Person months) | 1.9318
Requirement Stability Index | 90
Total Efforts in Person Months | 2.125
Phasewise Distribution
| Phasewise distribution (%) | Efforts | Span Time | Resource Loading | Remarks
Total (PDLC) Efforts (by converting size) | 4 | 2.125 | 0.15 | 14.1667
Requirements Analysis | 10 | 0.2125 | 0.3 | 0.70833
Design | 15 | 0.31875 | 0.45 | 0.70833
Coding | 34 | 0.7225 | 0.94 | 0.76862
Testing | 22 | 0.4675 | 0.61 | 0.76639
Release & Implementation | 7 | 0.14875 | 0.26 | 0.57212
Other factors
Project management | 4 | 0.085
QA | 2 | 0.0425
SCM, DP, training and other activities | 2 | 0.0425
Total Efforts for Other Factors in Person Months |  | 0.17
Total Efforts in Person Months |  | 2.295 | 2.56 | Total Span in Months
Note: * The phasewise distribution of % efforts has to be taken from the organizational goal It can be changed with proper justification for a project
Note on B6: Productivity per function in Person days
Note on B8: Total Coding Efforts in Person Months
Note on C11: RSI is an indicator available in the Organization Baseline. You may use RSI for calculating total efforts. This value is entered only for development projects.
Note on C15: Phasewise effort distribution is calculated based on the Phasewise distribution percentage
Note on D15: Phase wise Effort Distribution in Person Months
Note on E15: Span time in Months
Note on F15: No of resources required. The number is derived as Efforts in Person Months/ Span time in person Months
Note on G15: Enter the proper justification, if the Phasewise distribution percentage is different from Organization Goals.
Note on B17: Percentage efforts, calculated efforts , span time and resources required for the Requirements phase.
Note on B18: Percentage efforts, calculated efforts span time and resources required for the Design phase.
Note on B20: Percentage efforts, calculated efforts, span time and resources required for the Testing phase.
Note on B21: Percentage efforts, calculated efforts,span time and resources required for the Release & Implementation phase.
Note on C23: To be taken from Organization goals
Note on B24: Percentage efforts on Quality Assurance, efforts calculated for the project for QA activity, span time over which this activity is spread and resources required to execute the activity.
Note on C24: To be taken from Organization goals
Note on C25: Set on the basis of project requirement. Add the % of efforts required on SCM, Training, DP, Setup, etc..

## PCM estimation summary
PM-02-02 Ver 1.0 / 26-July-20 |  | PCM Estimation Summary
Size Estimation
Module/Function | Simple | Medium | Complex
Home Page | 3 | 0 | 2
About Us | 1 | 0 | 0
Payments | 2 | 0 | 1
Contact Us | 1 | 1 | 0
Our Services | 2 | 0 | 0
Chat-Bot | 0 | 1 | 2
Nav-Bar | 0 | 2 | 0
Footer | 0 | 1 | 0
Server Side Communication | 0 | 0 | 2
DBMS | 0 | 0 | 3
Module n
Total | 9 | 5 | 10
Complexity Index |  |  | 24.5
Note on B4: Enter the name of the function or Program
Note on C4: Enter the number of Simple programs based on the work breakdown worked out in PCM Details sheet
Note on D4: Enter the number of Medium programs based on the work breakdown worked out in PCM Details sheet
Note on E4: Enter the number of Complex programs based on the work breakdown worked out in PCM Details sheet

## Assumptions
PM-02-02 Ver 1.0 / 26-July-20 |  | Assumptions
Sl. No | Assumptions
No Assumptions Required because of requirement stability
N.B.The assumption list will be a part of each and every proposal.