## Change History
PM-02-04 Ver 1.0 / 26-July-20 |  |  |  | Change History
Project ID: |  | IAP-001 | Project Name : | INSURANCE AGENT PORTAL
Document Change History:
Ver.Rel. No | Release date | Modified By | Reviewed By | Approved By' | Modifications Done
1 | 2020-07-26 | Kartik, Varun, Shreyash | Simran | Jitesh | Base size(LOC), Effort Estimate sheets filled

## Base size(LOC)Estimation
PM-02-04 Ver 1.0 / 26-July-20 |  | Base size(LOC)Estimation
Sr. No. | Module Name |  | KLOC
1 | Home Page |  | 264
2 | About Us |  | 96
3 | Payments |  | 198
4 | Contact Us |  | 85
5 | Our Services |  | 95
6 | ChatBot |  | 92
7 | Nav-Bar |  | 72
8 | Footer |  | 73
9 | Server Side |  | 150
10 | DBMS |  | 350
Total |  |  | 1475
To identify module name refer to PCM Estimation Document.
Note on B3: Enter the serial number.
Note on C3: Enter the Module Name
Note on E3: Enter the number of Kilo Lines of Code.

## Standards
PM-02-04 Ver 1.0 / 26-July-20 |  |  | Standards
Unit: Hrs Per Program
Stage/Phase | COBOL/1000 LOC | PL/1 per 1000LOC | Assembly/1000 LOC
Inventory Analysis
System Impact Analysis
Detailed Impact Analysis
Conversion
Unit testing
Regression Testing
Total | 0 | 0 | 0

## Assumptions
PM-02-04 Ver 1.0 / 26-July-20 |  | Assumptions
Sr. No | Assumptions
1 | Site Navigation is Standardized, No user training required.

## Effort Estimate
PM-02-04 Ver 1.0 / 26-July-20 |  |  | Effort Estimate
Total Effort Estimation Sheet
Size of the Project in LOCs | 80
Productivity (Lines of Code/day) | 15
Efforts in Person Months | 0.24242
Requirement Stability Index | 71
Total Efforts in Person Months | 0.31273
Phase wise Effort Distribution
| Phasewise distribution(%) | Efforts | Span Time (in Months) | Resource Loading (No of Persons) | Remarks
Total efforts for PDLC | 5 | 0.31273 |  | 0
Requirements Analysis | 10 | 0.031273 | 0.3 | 0.10424
Design | 15 | 0.046909 | 0.4 | 0.11727
Coding | 34 | 0.10633 | 0.94 | 0.11311
Testing | 22 | 0.0688 | 0.61 | 0.11279
Release & Implementation | 7 | 0.021891 | 0.26 | 0.084196
Other factors
Project management | 4 | 0.012509
QA | 3 | 0.0093818
SCM, DP, training and other activities |  | 0
Total Efforts for Other Factors in Person Months |  | 0.021891
Total Efforts in Person Months |  | 0.33462 | 2.21 | Total Span in Months
Note: * The phasewise distribution of % efforts has to been taken from the organizational goal It can be changed with proper justification for a project
Note on C5: Take the productivity for entire PDLC from Organizational Goal for the platform
Note on C7: RSI is an indicator available in the Organization baseline.You may use RSI for calculating total efforts. This value is entered only for development projects.
Note on D11: Phase wise Effort Distribution in Person Months