## WAS
PM-01-02 Ver 2.01 / 29-Sep-04 |  |  | Work Allocation Sheet
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Sr. No. | PDLC Stage | Module Name | Work Item / Review Item | Type | Assigned To | Reference file ID / Bug ID | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Effort (Hrs) | Actual Effort (Hrs) | Number of Resources | Status | Dependencies | Remarks
Requirements Phase
1 | Requirement | Requirements Checklists | Filling Checklists | core work | TM | P-RC | 2020-07-13 | 2020-07-26 | 2020-07-13 | 2020-07-23 | 223 | 200 | 6 | Completed | Project Acceptance
2 | Requirement | Requirements Checklists | Review | Review | PL | P-RC | 2020-07-14 | 2020-07-27 | 2020-07-14 | 2020-07-24 |  |  |  | Completed
3 | Requirement | Documentation of requirements | Documentation | core work | TM | P-DR | 2020-07-15 | 2020-07-28 | 2020-07-15 | 2020-07-25 |  |  |  | Completed
4 | Requirement | Documentation of requirements | Review | Review | PL | P-DR | 2020-07-16 | 2020-07-29 | 2020-07-16 | 2020-07-26 |  |  |  | Completed
Estimation Phase
5 | Estimation | Estimation using Function Point Analysis | Filling Documents | core work | TM | P-FP | 2020-07-26 | 2020-08-01 | 2020-07-24 | 2020-07-28 | 130 | 120 | 6 | Completed | Requirement Documentation
6 | Estimation | Estimation using Function Point Analysis | Review | Review | PL | P-FP | 2020-07-27 | 2020-08-02 | 2020-07-25 | 2020-07-29 |  |  |  | Completed
7 | Estimation | Estimation using PCM | Filling Documents | core work | TM | P-PM | 2020-07-28 | 2020-08-03 | 2020-07-26 | 2020-07-30 |  |  |  | Completed
8 | Estimation | Estimation using PCM | Review | Review | PL | P-PM | 2020-07-29 | 2020-08-04 | 2020-07-27 | 2020-07-31 |  |  |  | Completed
9 | Estimation | Estimation using BS | Filling Documents | core work | TM | P-BS | 2020-07-30 | 2020-08-05 | 2020-07-28 | 2020-08-01 |  |  |  | Completed
10 | Estimation | Estimation using BS | Review | Review | PL | P-BS | 2020-07-31 | 2020-08-06 | 2020-07-29 | 2020-08-02 |  |  |  | Completed
Design Phase
11 | Design | Design-LLD | LLD | Core work | TM | P-HD | 2020-08-10 | 2020-08-16 |  |  | 335 |  | 8 | Planned | Requirement and Estimation Documentation
12 | Design | Design-LLD | Review | Review | PL | P-HD | 2020-08-10 | 2020-08-16 | [5 empty] | Planned
13 | Design | Design-DLD | DLD | Core work | TM | P-LD | 2020-08-10 | 2020-08-16 | [5 empty] | Planned
14 | Design | Design-DLD | Review | Review | PL | P-LD | 2020-08-10 | 2020-08-16 | [5 empty] | Planned
15 | Design | Design-HLD | HLD | Core work | TM | P-DD | 2020-08-10 | 2020-08-16 | [5 empty] | Planned
16 | Design | Design-HLD | Review | Review | PL | P-DD | 2020-08-10 | 2020-08-16 | [5 empty] | Planned
Development Phase
17 | Development | Home Page | Coding | Core work | TM | P-HP | 2020-08-17 | 2020-08-23 |  |  | 699 |  | 10 | Planned | Requirement, Design and Estimation Documentation
18 | Development | Home Page | Review | Review | PL | P-HP | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
19 | Development | About Us | Coding | Core work | TM | P-AU | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
20 | Development | About Us | Review | Review | PL | P-AU | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
21 | Development | Our Services | Coding | Core work | TM | P-OS | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
22 | Development | Our Services | Review | Review | PL | P-OS | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
23 | Development | Payments | Coding | Core work | TM | P-PS | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
24 | Development | Payments | Review | Review | PL | P-PS | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
25 | Development | Contact Us | Coding | Core work | TM | P-CU | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
26 | Development | Contact Us | Review | Review | PL | P-CU | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
27 | Development | Chat-Bot | Coding | Core work | TM | P-CB | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
28 | Development | Chat-Bot | Review | Review | PL | P-CB | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
29 | Development | Nav-Bar | Coding | Core work | TM | P-NB | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
30 | Development | Nav-Bar | Review | Review | PL | P-NB | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
31 | Development | Footer | Coding | Core work | TM | P-FT | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
32 | Development | Footer | Review | Review | PL | P-FT | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
33 | Development | Database Management of G-Forms input | Coding | Core work | TM | P-DG | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
34 | Development | Database Management of G-Forms input | Review | Review | PL | P-DG | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
35 | Development | Database Management Of Payment Details | Coding | Core work | TM | P-DP | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
36 | Development | Database Management Of Payment Details | Review | Review | PL | P-DP | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
37 | Development | Miscellaneous Database Management | Coding | Core work | TM | P-MM | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
38 | Development | Miscellaneous Database Management | Review | Review | PL | P-MM | 2020-08-17 | 2020-08-23 | [5 empty] | Planned
Testing Phase
39 | Testing | Home Page | Unit Testing | Core work | TM | P-HP | 2020-08-24 | 2020-08-30 |  |  | 460 |  | 11 | Planned | Requirement, Design and Estimation Documentation with Developed Software
40 | Testing | Home Page | Review | Review | PL | P-HP | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
41 | Testing | About Us | Unit Testing | Core work | TM | P-AU | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
42 | Testing | About Us | Review | Review | PL | P-AU | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
43 | Testing | Our Services | Unit Testing | Core work | TM | P-OS | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
44 | Testing | Our Services | Review | Review | PL | P-OS | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
45 | Testing | Payments | Unit Testing | Core work | TM | P-PS | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
46 | Testing | Payments | Review | Review | PL | P-PS | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
47 | Testing | Contact Us | Unit Testing | Core work | TM | P-CU | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
48 | Testing | Contact Us | Review | Review | PL | P-CU | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
49 | Testing | Chat-Bot | Unit Testing | Core work | TM | P-CB | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
50 | Testing | Chat-Bot | Review | Review | PL | P-CB | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
51 | Testing | Nav-Bar | Unit Testing | Core work | TM | P-NB | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
52 | Testing | Nav-Bar | Review | Review | PL | P-NB | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
53 | Testing | Footer | Unit Testing | Core work | TM | P-FT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
54 | Testing | Footer | Review | Review | PL | P-FT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
55 | Testing | Database Management of G-Forms input | Unit Testing | Core work | TM | P-DG | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
56 | Testing | Database Management of G-Forms input | Review | Review | PL | P-DG | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
57 | Testing | Database Management Of Payment Details | Unit Testing | Core work | TM | P-DP | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
58 | Testing | Database Management Of Payment Details | Review | Review | PL | P-DP | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
59 | Testing | Miscellaneous Database Management | Unit Testing | Core work | TM | P-MM | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
60 | Testing | Miscellaneous Database Management | Review | Review | PL | P-MM | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
61 | Testing | Integerated Modules | Integration testing | Core work | TM | P-IM-IT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
62 | Testing | Integerated Modules | Review | Review | PL | P-IM-IT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
63 | Testing | Integerated Modules | System Testing | Core work | TM | P-IM-ST | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
64 | Testing | Integerated Modules | Review | Review | PL | P-IM-ST | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
65 | Testing | Integerated Modules | Acceptance Testing | Core work | TM | P-IM-AT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
66 | Testing | Integerated Modules | Review | Review | PL | P-IM-AT | 2020-08-24 | 2020-08-30 | [5 empty] | Planned
Deployment Phase
67 | Deployment | Integerated Modules | Publishing site and setting up the database. | Core work | TM | P-IM-PL | 2020-08-31 | 2020-09-06 |  |  | 195 |  | 8 | Planned | Requirement, Design and Estimation Documentation with Developed Software
68 | Deployment | Integerated Modules | Review | Review | PL | P-IM-PL | 2020-08-31 | 2020-09-06 | [5 empty] | Planned
Maintainance Phase
69 | Maintainance | Integerated Modules | Maintainace of the site | Core work | TM | P-IM-MC | 2020-09-06 | 2020-12-05 |  |  | To be estimated later |  | 10 | Planned | Requirement, Design and Estimation Documentation and Developed Software
70 | Maintainance | Integerated Modules | Review | Review | PL | P-IM-MC | 2020-09-06 | 2020-12-05 | [5 empty] | Planned
Note on B6: ====== ID#AAAAGyBZEtA Administrator (2020-08-04 07:06:38) Running serial Number
Note on C6: ====== ID#AAAAGyBZEtI SSS (2020-08-04 07:06:38) PDLC Stage Name e.g. Requirement, Design, Coding, Testing, etc.
Note on D6: ====== ID#AAAAGyBZEtc SSS (2020-08-04 07:06:38) Module Name
Note on E6: ====== ID#AAAAGyBZEtU SSS (2020-08-04 07:06:38) Individual Work Item / Review item for the PDLC Stage and Module. E.g. Report Design, Screen Design, Function to be coded
Note on F6: ====== ID#AAAAGyBZEts Sundar (2020-08-04 07:06:38) Work allocation Review Rework Re-review
Note on G6: ====== ID#AAAAGyBZEtM SSS (2020-08-04 07:06:38) PL, Team Member to whom the work / review item is assigned
Note on H6: ====== ID#AAAAGyBZEtE Sundar (2020-08-04 07:06:38) Reference file ID / Bug ID for Review, Rework, Re-review
Note on I6: ====== ID#AAAAGyBZEuA SSS (2020-08-04 07:06:38) Planned start date for the work item
Note on J6: ====== ID#AAAAGyBZEtY SSS (2020-08-04 07:06:38) Planned end date for the Work Item
Note on K6: ====== ID#AAAAGyBZEt8 SSS (2020-08-04 07:06:38) Actual Start date
Note on L6: ====== ID#AAAAGyBZEtw SSS (2020-08-04 07:06:38) Actual end date for the work item
Note on M6: ====== ID#AAAAGyBZEt4 SSS (2020-08-04 07:06:38) Planned Effort for the work item in Hrs
Note on N6: ====== ID#AAAAGyBZEt0 SSS (2020-08-04 07:06:38) Actual Effort for the work item in Hrs
Note on O6: ====== ID#AAAAGyBZEtk ISD (2020-08-04 07:06:38) Number of resources allocated for the work item
Note on P6: ====== ID#AAAAGyBZEtg SSS (2020-08-04 07:06:38) Planned, Started, Completed, Postponed, Cancelled, Transferred (when the work item is transferred from one resource to another. In this case retain the first allocation entry with Transferred status with Actual End Date showing transfer date. Add new entry for showing new resource name and new planned date.
Note on Q6: ====== ID#AAAAGyBZEto skk-prj (2020-08-04 07:06:38) Mention the serial nos. Of work items whose completion is prerequisite for this work item.
Note on R6: ====== ID#AAAAGyBZEtQ Administrator (2020-08-04 07:06:38) Explanatory Text, if required, for the entry
Note on O8: ====== ID#AAAAKEIE6-Q jitesh mishra (2020-08-06 06:28:32) 5 team members, Project Acceptance Documentation.
Note on O13: ====== ID#AAAAKEIE6-Y jitesh mishra (2020-08-06 06:29:54) 5 team members,Requirement Documentation.
Note on O20: ====== ID#AAAAKEIE7MQ jitesh mishra (2020-08-06 07:19:44) 5 Team Members, Requirement Documentation, Estimation Documentation, Star UML
Note on O27: ====== ID#AAAAKEIE7NI jitesh mishra (2020-08-06 07:22:01) 5 Team Members, Requirement Documentation, Estimation Documentation, Angular 10,Visual Studio Code, Git-Hub.
Note on O50: ====== ID#AAAAKEIE7Ng jitesh mishra (2020-08-06 07:24:23) 5 Team Members, Requirement Documentation, Estimation Documentation, Angular 10,Google Insights, Git-Hub and server
Note on O79: ====== ID#AAAAKEIE7PU jitesh mishra (2020-08-06 07:28:15) 5 Team Members, Requirement Documentation, Estimation Documentation and Server.
Note on O82: ====== ID#AAAAKEIE7Po jitesh mishra (2020-08-06 07:31:49) 5 Team Members, Requirement Documentation, Angular 10,Visual Studio Code, Git-Hub, Google Insights.