## Staff requirement
PM-01-05 Ver 1.0 / 02-Aug-20 |  |  | Resource Register: Staff Requirement
Project ID: |  | IAP - 001 | Project Name: |  | Insurance Agent Portal
SBU: |  | Jitesh Mishra | Total no. of persons: |  | 5
Location: |  | Offshore | Estimated person months: |  | 2.56
Author(s): |  | Simran Kumari (PM/ PL) | Total person months requested: |  | 12.8
Role | No. of persons | Skills Required |  | Required by date | Location | Requirement duration | Remarks
|  | IT Skills | Domain Experience
QL | 1 | Six - Sigma Green Belt | None | 2020-08-13 | Offshore | 3
ML | 1 | Angular | None | 2020-08-13 | Offshore | 3
HQA | 1 | Six - Sigma Green Belt | None | 2020-08-13 | Offshore | 3
TM | 3 | Full Stack Development | None | 2020-08-13 | Offshore | 3
DBA | 1 | Angular Developer and Database Maintenance | None | 2020-08-13 | Offshore | 3
CL | 1 | Angular, Database Management | None | 2020-08-13 | Offshore | 3

## Staff register
PM-01-05 Ver 1.0 / 02-Aug-20 |  |  | Resource Register: Staff
Project ID: |  | IAP-001 | Project Name: |  | INSURANCE AGENT PORTAL |  | Training Plan / Log
SBU: |  | Jitesh Mishra | Total no. of persons: |  | 5 |  | RBT (for PL, PM, TM, QL, etc) | Project induction | Organizational induction | MPP / MPC | Rational Rose/UML | Domain knowledge | HTML | CSS | ANGULAR
Name of PM: |  | Simran Kumari | Current staff strength: |  | 5
Name of PL: |  | Simran Kumari | Last updated on: |  | 2020-08-01
[16 empty] | Appraisal Done (Includes skill appraisal for BMC centers) (Y/N) | Update skills in HumaRIS/Skill rating template for PCAP (Y/N)
Sr. No. | PS No. | Staff Name | Location | Roles | From Date | To Date
1 | JM-01-01 | Jitesh Mishra | Offshore | SM | 2020-07-08 | 2020-12-05 | C | A | C | C | C | C | W | W | W | No | Yes
2 | VK-01-01 | Varun Khadayate | Offshore | TM\ML | 2020-07-08 | 2020-12-05 | C | A | C | W | A | C | C | C | C | No | Yes
3 | KP-01-01 | Kartik Padave | Offshore | TM\CL\DBA | 2020-07-08 | 2020-12-05 | C | A | C | W | A | C | C | C | C | No | Yes
4 | SK-01-01 | Simran Kumari | Offshore | PM\PL | 2020-07-08 | 2020-12-05 | C | A | C | C | C | C | W | W | W | No | Yes
5 | SA-01-01 | Shreyash Agrawal | Offshore | TM\QL\HQA | 2020-07-08 | 2020-12-05 | C | A | C | W | A | C | C | W | W | No | Yes
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## HW & SW requirement
PM-01-05 Ver 1.0/ 01-Aug-20 |  | Resource Register: HW, SW and Network
Project ID: |  | IAP-001 | Project Name: |  | INSURANCE AGENT PORTAL
Author(s): |  | Simran Kumari | Accepted on: |  | 2020-08-02
Reviewer: |  | Jitesh Mishra | Last updated on: |  | 2020-08-01
Development Environment
Hardware
Sr. No. | Purpose | Configuration | Quantity | Owned by | Remarks | Required by date | Received by date
1 | Web server | Wifi bandwidth with 802.11b, 2.4Ghz, 11 Mbps | 1 | LTI |  | 2020-08-02 | 2020-08-02
2 | Database Server | Basic configuration | 1 | LTI |  | 2020-08-02 | 2020-08-02
3
4
5
6
7
8
Software
Sr. No. | Name of the software | Version/release details | No. of licenses | Owned by | Remarks | Required by date | Received by date
1 | Angular | 10 | 3 | 3rd party | Open Source | 2020-08-02 | 2020-08-02
2 | Visual Studio Code | 1.4.7.3 | 3 | 3rd party | Open Source | 2020-08-02 | 2020-08-02
3 | Star UML | 17.12 | 3 | 3rd party | Open Source | 2020-08-02 | 2020-08-02
4
5
6
7
8
Test environment
Hardware
Sr. No. | Purpose | Configuration | Quantity | Owned by | Remarks | Required by date | Received by date
1 | Same as development environment
2
3
4
5
6
7
8
Software
Sr. No. | Name of the software | Version / release details | No. of licenses | Owned by | Remarks | Required by date | Received by date
1 | Same as development environment
2
3
4
5
6
7
8
Tools
Sr. No. | Purpose | Tool name, Version / release details | No. of licenses | Owned by | Remarks | Required by date | Received by date
1 | Development,Testing Phases and Performance assurity | GitHub | 3 | 3rd party | Open Source | 2020-08-02 | 2020-08-02
2 | Testing Phases and Performance assurity | Google Insights | 3 | 3rd party | Open Source | 2020-08-02 | 2020-08-02
3
4
5
6
7
8
Network Requirements
Sr. No. | Description of connectivity | Purpose | Bandwidth | Required by date | Received by date | Required upto date | Remarks
1 | Database Server | Used in Development, Testing, Release and Implemetation phases of project | 60 Mbps | 2020-08-02 | 2020-08-02 | 2020-12-05
2 | Web Server | Used in Development, Testing, Release and Implemetation phases of project | 11 Mbps | 2020-08-02 | 2020-08-02 | 2020-12-05
3
4