## Risk Monitoring Log
PM-06-01 Ver 1.0 / 2-Aug-20 |  |  |  |  | Risk Monitoring Log
Project ID: |  | IAP-001 |  | Project Name: |  | Insurance Agent Portal
Sr. No. | Risk | Risk Identification Date | Risk Assessment Date | Anticipated Risk? (Yes/No) | Phase | Risk Type | Risk Response Type | Risk Action Type | Status of Risk | Anticipated Impact | Action Plan | Date of completion of Action | Probability | Impact (1-5) | Risk Index (Probability x Impact) | Risk Occurrence |  | Remarks
[16 empty] | Actual Impact | Actual Action
1 | Undocumented Assumptions | 2020-08-02 |  | Yes | General | Requirements | Contingency | Avoid | Elapsed | E+C+Q | Reviewing and making documents throughly. |  | 0.3 | 2 | 0.6
2 | Business requirements as functional requirements | 2020-08-02 |  | Yes | Requirement | Requirements | Contingency | Avoid | Elapsed | E+Q | Reviewing and making documents throughly. |  | 0.3 | 4 | 1.2
3 | Inadequate validation | 2020-08-02 |  | Yes | General | People | Contingency | Avoid | Elapsed | E+S+Q | Reviewing and making documents throughly. |  | 0.3 | 4 | 1.2
4 | Complicated Design | 2020-08-02 |  | Yes | Design | Internal | Contingency | Avoid | Monitored | E+S+C+Q | Making a simpler wireframe with simple design and all the requirements |  | 0.5 | 3 | 1.5
5 | External Outputs | 2020-07-30 | 2020-07-30 | No | General | Estimation | Preventive | Accept | Closed | E+C | Make required changes | 2020-07-30 | 0.3 | 2 | 0.6 | S | Made Required changes
6 | Modules are developed by different programmers | 2020-08-02 |  | Yes | Development | People | Contingency | Avoid | Monitored | S+C+Q | There should be a clear communication between developers. |  | 0.3 | 2 | 0.6
7 | High fault rate in newly designed components | 2020-08-02 |  | Yes | Development | People | Contingency | Avoid | Monitored | E+S+Q | Developers should throughly check their code before passing it on to next phase. |  | 0.3 | 3 | 0.9
8 | Omissions or oversights while integrating different modules | 2020-08-02 |  | Yes | Development | Internal | Contingency | Avoid | Monitored | S+Q | Reviewing integrated module throughly. |  | 0.3 | 4 | 1.2
9 | Server Crash | 2020-08-02 |  | Yes | General | External | Contingency | Avoid | Monitored | E+S+C+Q | Follow the BSD Plan |  | 0.3 | 4 | 1.2
10 | [14 empty] | 0

## Guidelines
Guidelines for using RML template
Note: RML template helps in keeping track of identified and materialized risks, their classification, assessment, prioritization, likely impact and the action plans for risk response. This also helps in keeping track of changes in risk priorities and action plans.
Field name | Guideline
Risk | Describe the Risk condition (E.g. requirements are not detailed with sufficient clarity) and consequence (E.g. could result in scope creep)
Risk Identification Date | Mention the date on which the risk was identified.
Risk Assessment Date | Mention the last date on which the risk was assessed / monitored.
Anticipated Risk? (Yes/No) | If the risk was identified earlier, mention Yes. If the risk was identified only after occurrence mention No.
Phase | Helps in identification of the project phase during which the risk is likely to impact. It could be: 1) General (Any time) 2) Requirement 3) Design 4) Development 5) Testing 6) Rel. & Imp. 7) Warranty
Risk Type | Helps in classifying risk for better tracking and response planning: 1) Requirements 2) Technology 3) Estimation 4) People 5) Internal 6) Tools 7) Customer related 8) Contract (or Legal) 9) External - (External environment like Regulations, Visa procedures) 10) Others - Any risk which does not fall in any one of the above risks
Risk Response Type | Select the type of response planned for the risk. It could be Preventive or Contingency response. Refer to Probability-Impact Matrix
Risk Action Type | Avoid – Execute action plan prior to occurrence to avoid risk totally. Ideal for Risks with very high impact
Remove – Remove risk in subsequent phases after occurrence of risk
Reduce - Reduce risk partially with appropriate action plan
Transfer - Transfer the impact to others like Customer and business partners (in terms of exclusions, etc.) Taking appropriate insurance is also a transfer strategy.
Accept - Accept the impact of risk. Select when the Risk index is low or when Cost of action plan exceeds the benefits.
Status of Risk | Enter the status of Risk on the date of assessment: 1) Monitored - When risk is still open 2) Impacted - Already impacted the project 3) Elapsed - Passed without impact 4) Closed - Closed after impact
"Anticipated Impact" and "Actual Impact" (on the project) | These helps to qualitatively evaluate impact (Anticipated / Actual) in terms of Effort, Cost and Schedule individually or in combination. Approximate cost, schedule and effort are worked out by PM in arriving at action plans for identified risk / evaluating actual impact on materialized risk. Note: Select cost only when there is a direct expense involved (Eg. Additional HW for testing, Third party testing, Additional tools procurement, Extended on-site non-billable stay), though effort involves cost.
Action Plan | Action Plan is the Risk response to be identified keeping in mind the Risk index and practical options possible. “Action Plan must be decided after considering the expected benefits and the cost of solving the problem” Note: Identify the activities and include in Project schedule for all action plans to be executed.
Date of completion of action plan | Mention the actual date on which the action plan for preventing risk was completed.
Probability | Select the probability of occurrence of risk with your judgment / in consultation with an expert / SM 0.3 - Low 0.5 - Medium 0.9 - High
Impact | Select the Severity of Impact of the risk 5-Very High 4-High 3-Medium 2-Low 1-Very Low
Risk Index | Product of Probability and Impact gives Risk Index. This helps to prioritize the risks. Refer to Probability - Impact Matrix for more details
Actual Action | Narrate the actual action taken for minimizing the impact of a materialized risk.
Remarks | Briefly describe the actual impact of materialized risk and additional information (if any) in remarks.
Note | Changing Risk perception during tracking:
Risk perceptions for some of the identified risks changes over a period of time. It could be an increase in risk or changing scenario reducing the risk. Hence some risks keep moving in and out of risk radar of high priority risks of Senior Managers.
In order keep visible track of changes in Risk response type / Action plan and Risk index based on revised risk assessments, enter the revisions in the next line with an intermediate Sl.No. Eg. For risk in Sl. No 2, the PM wants to revise the Action plan and Risk Index after some time. He has to enter new values in these columns by inserting a row. Sl. No. for this row will be 2.1. This provides history of changes in risk perception and related fields.

## Sample Risk Monitoring Log
PM-06-01 Ver 2.1 / 25-Jun-04 |  |  |  |  | Risk Monitoring Log
Project ID: |  | I1127 |  | Project Name: |  | Sample
Sr. No. | Risk | Risk Identification Date | Risk Assessment Date | Anticipated Risk? (Yes/No) | Phase | Risk Type | Risk Response Type | Risk Action Type | Status of Risk | Anticipated Impact | Action Plan | Date of completion of Action | Probability | Impact (1-5) | Risk Index = (Probability x Impact) | Risk Occurrence |  | Remarks
[16 empty] | Actual Impact | Actual Action
1 | Requirements are not detailed with sufficient clarity. Could result in scope creep. | 2003-07-01 | 2003-07-01 | Yes | Requirement | Requirements | Preventive | Avoid | Monitored | E+S+C | Send one domain and one technical expert to Customer's place for 15 days for detailed study of requirements and obtain signoff. |  | 0.9 | 4 | 3.6
1.1 | - Change of Action plan for 1.0 | 2003-07-15 | 2003-08-01 |  |  |  |  | Reduce | Closed |  | Have daily discussion with Customer. Develop a Prototype in 10 days and get approval | 2003-08-01 | 0.9 | 4 | 3.6 | E | Prototype developed and accepted by customer. | Effort for prototype development taken-up with customer as change request.
2 | Some team members are new to .net Technology. Might affect schedule and quality | 2003-07-05 | 2003-08-01 | Yes | Development | People | Preventive | Reduce | Monitored | E+S | Train the team members in .net. Allocate inexperienced staff to wok under experienced staff | 2003-07-30 | 0.5 | 3 | 1.5
3 | Link down time might affect the schedule | 2003-07-10 | 2003-07-10 | Yes | General | Internal | Contingency | Accept | Monitored | S | Inform customer via phone and schedule the work for late hours after link is UP. |  | 0.3 | 2 | 0.6
4 | [5 empty] | Others | [8 empty] | 0
5 | [14 empty] | 0
6 | [14 empty] | 0
7 | [14 empty] | 0
8 | [14 empty] | 0
9 | [14 empty] | 0
10 | [14 empty] | 0

## PI Matrix
Probability-Impact Matrix
Probability |  | Risk Index
High | 0.9 | 0.9 | 1.8 | 2.7 | 3.6 | 4.5
Medium | 0.5 | 0.5 | 1 | 1.5 | 2 | 2.5
Low | 0.3 | 0.3 | 0.6 | 0.9 | 1.2 | 1.5
|  | 1 | 2 | 3 | 4 | 5 | Impact
|  | Very Low | Low | Med | High | Very High
Risk Index | Recommended action
High | High - Requires PMs focus and SMs active participation in risk management. Consider preventive risk response as the preferred option.
Medium | Medium - Requires PMs attention and SMs guidance in risk management. Consider preventive risk response if the cost of response is low. Else have contingency response ready.
Low | Low - Requires PMs attention. Consider contingency response to execute when the risk occurs. Alternatively accept the impact of risk if it is not worth responding.