## Review Log
PD-07-01 Ver 1.0 / 25-Jul-20 |  |  |  | Review Log
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Reviewable item: |  | PM-01-05-Resource_Register | Author(s): | Simran Kumari
Reviewed by: |  | Jitesh Mishra | Reviewed on: | 2020-08-02
Moderator: |  | Simran Kumari | Accepted on: | 2020-08-02
Version of reviewable: |  | 1 | No. of defects detected: | 2
Reviewable LOC/Pages: |  | 1 | LOC/Pages to be reworked: | 1
Review stage: |  | PS | Follow up action: | Verify
Details of defects:
Sr. No. | Doc. Id/ Program Id | Location | Description, Optional for document reviews | Category, By Reviewer | Severity, By Reviewer | Cause, by Author | Introduced at | Status | Fixed On Date | Closed/ Transferred On, Date | Remarks
1 | PM-01-05-Resource_Register | Staff Requirement | Requirement Duration | MS | 3 | IK | PM | Fixed | 2020-08-04 | 2020-08-05
2 | PM-01-05-Resource_Register | HW & SW Requirement | Requirements are not mentioned properly | MS | 3 | NA | PM | Fixed | 2020-08-04 | 2020-08-05

## Guidelines-Cause and Category
Note : 1. IU and DE categories removed. IU gets covered under LO. DE error gets covered under IF, LO, DA 2. CL and CP added 3. CC has been removed. CC type of comments can be classified under ST or CP
Details of defect category:
Code | Description | New guidelines | Applicable
MS | Missing | Missing Design (of required functionality). A certain requirement is covered nowhere in the design. Missing Implementation (of planned functionality). A certain part of a design was not implemented. Missed Errorhandling. An error case was not handled in the program (or not handled properly). Missing Assignment. A single variable was not initialized or updated. Only one statement needs to be added. Missing Call. A single method call is missing. Only one statement needs to be added. | PMP review Requirement review Design review Testcase review Code review Testing
IF | Interface | Interface Capability. The design of an interface is wrong, so that the interface does not provide the functionality that it must provide. Interface Specification. The specification of an interface is wrong, so that the parameters involved cannot transfer all of the information required for providing the intended functionality. This is a less fundamental variant of IC: Only parameters need be added. Interface Description. The description of an interface is incomplete, wrong, or misleading, the description of a variable or class attribute or data structure not correct. Interface Use. An interface was used wrongly, i.e., in such a way as to violate the interface specification. | Requirement Review Design Review Code Review Testing
LO | Program Logic | Wrong Algorithm: The entire logic in a method is wrong and cannot provide the desired functionality. Wrong Expression: An expression (in an assignment or method call) computes the wrong value.A boolean expression was wrong. Objects or their names were confused. The wrong method, attribute, or variable was used. Wrong Type: Two `similar' types were confused. Boundary Related errors: Calculation Error: Outdated constants, wrong parentheses, truncation, incorrect conversion from one Initialization Errors: Failure to set a data item, loop variables, initialize pointers, failure to clear flags Control Flow errors: Programs runs amok, stops, loop error If then else, multiple cases error: Wrong inequalities(e.g.,> instead of >=), Comparison sometimes yields wrong result | Design Code review Testing
OP | Optimization/Performance | Optimal usage is lacking Performance is not upto the mark. Design will adversely affect the product's performance. Optimization w.r.t programming language. Multiple calls to procedures to be replaced by fewer calls in the code. | Requirement review Design review Code review Testing Bugs
DA | Data | 1. Problems when passing data between routines: Parameter list variables out of order or missing, Data type errors, Aliases and shifting interpretations of the same areas of memory, Misunderstood data values, Failure to clean up data on exception-handling exit, Outdated copies of data, Related variables get out of synch, Local setting of global data, Global use of local variables, Wrong value from a table 2. Data Boundaries : Unterminated null terminated strings, Read/Write past end of a data structure , or an element in it 3. Read outside the limits of a message buffer : Compiler padding to word boundaries, Compiler padding to word boundaries, Value stack under/overflow, 4. Messaging : Messages sent to wrong process or port, Failure to validate an incoming message, Lost or out of synch messages 5. Data storage corruption: Overwritten changes, Data entry not saved, Too much data for receiving process to handle, Overwriting a file after an error exit or user abort | Coding Review Testcase Review Testing
ST | Standards | Item under review does not comply with the project or the organization standards | Requirement review Design review Code review Testing
US | Usability Errors | Panels, messages, help being reviewed are in error. Their design/implementation will adversely affect usability of the product. | Design Code review Testing
SG | Suggestion. | If the defect reported is a suggestion. | All
NR | Not Relevant/ Redundant/ error in supporting documents | If the unit within a review item is irrelevant to the scope of the item or the unit within a review item is redundant. For e.g.., Unused Paragraphs, Variables and unreachable statements An error due to error in supporting documents. | Requirement review Design review Code review Testing
CL | Clarity | Clarity Needed For e.g.., If the test cases / comments in source code, variable naming / paragraph naming etc doesn't give clarity to the reviewer. | All Documents
CP | Cosmetic/ Presentation | Cosmetic/ Presentation Grammar / spelling . For e.g.., If the screen layout needs to be improved. Say alignments, color, fonts etc which do not affect the requirement. Spelling mistake in Comments and Comment not proper | Code review Testing All documents
Note : Removed RW TR is subcategorized into IK, IS Added External factor(EF), Improper Language(IL), Not applicable(NA) causes Added LT cause : This cause to be used only with MS, ST, CP, CL type of errors
Details of defect cause:
Code | Description | Guidelines | Applicable
CO | Communication Gap | Communication Gap Something not communicated or some misleading information communicated.
OV | Oversight | Ignorance - Forgot something because did not know about it -Did something wrong, although knew how to do it right Typo Did something trivial wrong typing mistake For E.g.., if the author commits the error inspite of the standards documents, Checklists, Requirements and other inputs being properly conveyed.
UN | Understanding Error | Understanding Error Failure to understand the Requirement / Specification / Standards.
EF | External Factor | External factor - Limitations of Architecture : The bug IS The result of The limitation in The Architecture used for development. - Errors in base system : This IS specifically Applicable for Porting projects. - Inadequate system/application knowledge : Indaquate application/system knowledge. This could be when we do not have complete knowledge of The system being developed
IK | Inadequate knowledge/ experience | The software professional does not have adequate knowledge or experience . This could be because training not given, training not effective
IS | Inadequate technical skills | Technical skills required to perform the activity inadequate
NA | Not Applicable | Not Applicable Applicable only for Suggestion defect category. | For SG category only
Details of defect severity:
1 | Fatal | Show Stoppers. This may include GPF, System hangs because of the software.
2 | Serious(Operation degraded) | This is not a shop stopper. This may include inconsistent with the Functional Requirements or data rendered is inconsistent and user cannot proceed with successful test.
3 | Minor (Inconvenient usage) | These error allows the functionality of the software with some work around.
4 | Cosmetic | Improve user interface