## TEAM WORK
WEEKLY REPORT
Project ID: | IAP-001 |  | Project Name: | Insurance Agent Portal
Last Updated Date: | 2020-07-22 |  | Lab Activity: | Requirement Analysis
Modified By | Varun Khadayate, Shreyash Agarwal, Kartik Padave,Simran Kumari |  | Authorised By: | Jitesh Mishra
WEEK 1
TEAM WORK
DATE / DAY | TASK | DURATION
09-07-2020 (Thrusday) | Preparing questionnaire | 43 min
| Requirement gathering via client interview | 30 min
| Finalization requirement with customer after discussing with the team | 5 min
10-07-2020 (Friday) | Documenting finalised requirements | 1 hr
11-07-2020 (Saturday) | Understanding Requirement gathering and analysis document | 2 hr
| Individual task allotment | 2 hr
12-07-2020 (Sunday) | Merging of individually created screen | 1 hr 20 min
13-07-2020 (Monday) | Completing the requirement gathering checklist | 1 hr 35 min
14-07-2020 (Tuesday) | Finishing Requirement gathering checklist by team 1 | 1 hr 25 min
WEEK 2
TEAM WORK
DATE / DAY | TASK | DURATION
16-07-2020 (Thrusday) | Reviewing the requirement gathering checklist by entire team | 35 min
| Completion of Requirement Specification Review Checklist reviewing | 1hr 5 min
17-07-2020 (Friday) | Task allotement for PD-01-01-RS to team 1 and 2 | 31 min
18-07-2020 (Saturday) | PD-01-01-RS partial completion | 5 hr
19-07-2020 (Sunday) | RTT completion and reviewing | 1hr 37 min
| PD-01-01-RS completion | 3 hr 15 min
20-07-2020 (Monday) | Final touchup to the website | 1 hr
21-07-2020 (Tueday)
22-07-2020 (Wednesday) | Weekly Report Documentation | 2 hr 15 min
Project ID: | IAP-001 |  | Project Name: | Insurance Agent Portal
Last Updated Date: | 2020-07-26 |  | Lab Activity: | Estimation Process
Modified By | Varun Khadayate, Shreyash Agarwal, Kartik Padave, Simran Kumari |  | Authorised By: | Jitesh Mishra
WEEK 3
TEAM WORK
DATE / DAY | TASK | DURATION
24-07-2020 (Friday) | Estimation Excel Sheet Allotment | 11 min 37 sec
| Partial Completion of PM-02-01-FP | 2hr 17min
25-07-2020 (Saturday) | Completion of (PM-02-01-FP) | 1 hr 34 min
26-07-2020 (Sunday) | Completion of (PM-02-04-BS) | 25m 36s
| Completion of (PM-02-02-PCM) | 3h 42m
Project ID: | IAP-001 |  | Project Name: | Insurance Agent Portal
Last Updated Date: | 2020-08-05 |  | Lab Activity: | Project Planning
Modified By | Varun Khadayate, Shreyash Agarwal, Kartik Padave, Simran Kumari |  | Authorised By: | Jitesh Mishra
WEEK 4
TEAM WORK
DATE / DAY | TASK | DURATION
31-07-2020 (Friday) | Analyzing PM-01-Prj_Planning | 30 min
| Allocation of PM-01-Prj_Planning and partial completion of PM-01-01-PMP by individual sub group | 1hr 46 min
01-08-2020 (Saturday) | Partial Competion on PM-01-05-Resource_Register and PM-01-01-PMP | 6 hr 16 min
26-07-2020 (Sunday) | Completion on PM-01-05-Resource_Register, PM-01-01-PMP and PM-01-01-PMP | 7 hr 17 min

## INDIVIDUAL WORK
INDIVIDUAL WEEKLY REPORT
Project ID: | IAP-001 |  |  | Project Name: | Insurance Agent Portal
Last Updated Date: | 2020-07-22 |  |  | Lab Activity: | Requirement Analysis
Modified By | Varun Khadayate, Shreyash Agarwal, Kartik Padave,Simran Kumari |  |  | Authorised By: | Jitesh Mishra
ROLES | NAME | DATE | WORKING HOURS | TASK
CL | KARTIK PADAVE | 2020-07-09 | 2 HR | Analyzing Requirement Specification Document
|  | 2020-07-10 | 1 HR 30 MIN | Documenting finalised requirements
|  | 2020-07-11 | 3 HR | Coding work for Header Footer of the portal
|  | 2020-07-12 | 2 HR | Explaining the code and merging
|  | 2020-07-13 | 3 HR | Working on Requirement Gathering Checklist
|  | 2020-07-14 | 3 HR | Finishing Requirement Gathering Checklist
|  | 2020-07-15 | 1 HR 30 MIN | Coding work for the portal
|  | 2020-07-16 | 1 HR 30 MIN | Requirement Specification Review Checklist completion
|  | 2020-07-17 | 2 HR | partial completion of RS document
|  | 2020-07-18 | 4 HR
|  | 2020-07-19 | 4 HR | PD-01-01-RS completion
|  | 2020-07-20 | 2 HR | Final touchup to the website
|  | 2020-07-21 | 1 HR | Miscellaneous
TM | SHREYASH AGARWAL | 2020-07-09 | 30 MIN | Analyzing Requirement Specification Document
|  | 2020-07-10 | 30 MIN | Documenting finalised requirements
|  | 2020-07-11 | 30 MIN | Coding work for Contact US of the portal
|  | 2020-07-12 | 2 HR | Explaining the code and merging
PL | SIMRAN KUMARI YADAV | 2020-07-09 | 1 HR 45 MIN | Analyzing Requirement Specification Document
|  | 2020-07-10 | 30 MIN | Documenting finalised requirements
|  | 2020-07-11 | 5 HR | Coding work for Payment Deatils of the portal
|  | 2020-07-12 | 1 HR | Explaining the code and merging
|  | 2020-07-13 | 1 HR 35 MIN | Working on Requirement Gathering Checklist
|  | 2020-07-16 | 35 MIN | Finishing Requirement Gathering Checklist
|  | 2020-07-17 | 45 MIN | Coding work for the portal
|  | 2020-07-18 | 1 HR 5 MIN | Requirement Specification Review Checklist completion
|  | 2020-07-19 | 45 MIN | partial completion of RS document
|  | 2020-07-22 | 3 HR 20 MIN | PD-01-01-RS completion
ML | VARUN KHADAYATE | 2020-07-09 | 30 MIN | Analyzing Requirement Specification Document
|  | 2020-07-10 | 45 MIN | Documenting finalised requirements
|  | 2020-07-11 | 1 HR | Coding work for About Us of the portal
|  | 2020-07-12 | 3 HR | Explaining the code and merging
|  | 2020-07-13 | 1 HR 35 MIN | Working on Requirement Gathering Checklist
|  | 2020-07-16 | 25 MIN | Finishing Requirement Gathering Checklist
|  | 2020-07-17 | 10 MIN | Requirement Specification Review Checklist completion
|  | 2020-07-18 | 40 MIN | partial completion of RS document
|  | 2020-07-22 | 3 HR 20 MIN | PD-01-01-RS completion
PM | JITESH MISHRA | 2020-07-08 | 6 HR 30 MIN | Analyzing Requirement Specification Document, Creating Wireframe for the Portal
|  | 2020-07-11 | 4 HR 30 MIN | Coding work for Homepage of the portal
|  | 2020-07-12 | 7 HR 30 MIN | Merging the Codes and partial creation of final website
|  | 2020-07-15 | 30 MIN | Documentation work
|  | 2020-07-16 | 4 HR | Reviewing the requirement gathering checklist
|  | 2020-07-20 | 3 HR | Final touchup to the website
|  | 2020-07-21 | 2 HR 30 MIN | Final touchup to the website
|  | 2020-07-22 | 3 HR 20 MIN | Weekly Report Documentation
Project ID: | IAP-001 |  |  | Project Name: | Insurance Agent Portal
Last Updated Date: | 2020-07-26 |  |  | Lab Activity: | Estimation Process
Modified By | Varun Khadayate, Shreyash Agarwal, Kartik Padave,Simran Kumari |  |  | Authorised By: | Jitesh Mishra
ROLES | NAME | DATE | WORKING HOURS | TASK
CL | KARTIK PADAVE | 2020-07-24 | 1 hr | Estimation Excel Sheet Analysis (EO)
|  | 2020-07-25 | 30 min | GSC
TM | SHREYASH AGARWAL | 2020-07-24 | 1 hr | Estimation Excel Sheet Analysis (EI)
|  | 2020-07-25 | 30 min | Caper Jone Table, Reference Table
PL | SIMRAN KUMARI YADAV | 2020-07-24 | 1 hr | Estimation Excel Sheet Analysis (EIF)
|  | 2020-07-25 | 30 min | Work Breakdown (PCM)
RSI CALCULATION
|  |  | 45 min | Review Log
|  | 2020-07-26 | 10 min | Updation of Weekly Work Report
ML | VARUN KHADAYATE | 2020-07-24 | 1 hr | Estimation Excel Sheet Analysis (ILF)
|  |  | 35 min | Minutes Of Meeting
|  | 2020-07-25 | 30 min | Effort Estimate
PM | JITESH MISHRA | 2020-07-24 | 1 hr | Estimation Excel Sheet Analysis (EQ)
|  | 2020-07-25 | 30 min | FPA Summary Table
|  |  | 45 min | Review Log