## WAS
PM-01-02 Ver 2.01 / 29-Sep-04 |  |  | Work Allocation Sheet
Project ID: |  | IAP-001 | Project Name: | INSURANCE AGENT PORTAL
Sr. No. | PDLC Stage | Module Name | Work Item / Review Item | Type | Assigned To | Reference file ID / Bug ID | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Planned Effort (Hrs) | Actual Effort (Hrs) | Number of Resources | Status | Dependencies | Remarks
1 | Design | Design-HLD | HLD | Core work | TM | P-HD | 2020-08-10 | 2020-08-16
2 | Design | Design-HLD | Review | Review | PL | P-HD | 2020-08-10 | 2020-08-16
3 | Design | Design-LLD | LLD | Core work | TM | P-LD | 2020-08-10 | 2020-08-16
4 | Design | Design-LLD | Review | Review | PL | P-LD | 2020-08-10 | 2020-08-16
5 | Design | Design-DLD | DLD | Core work | TM | P-DD | 2020-08-10 | 2020-08-16
6 | Design | Design-DLD | Review | Review | PL | P-DD | 2020-08-10 | 2020-08-16
7 | Development | Home Page | Coding | Core work | TM | P-HP | 2020-08-17 | 2020-08-23
8 | Development | Home Page | Review | Review | PL | P-HP | 2020-08-17 | 2020-08-23
9 | Development | About Us | Coding | Core work | TM | P-AU | 2020-08-17 | 2020-08-23
10 | Development | About Us | Review | Review | PL | P-AU | 2020-08-17 | 2020-08-23
11 | Development | Our Services | Coding | Core work | TM | P-OS | 2020-08-17 | 2020-08-23
12 | Development | Our Services | Review | Review | PL | P-OS | 2020-08-17 | 2020-08-23
13 | Development | Payments | Coding | Core work | TM | P-PS | 2020-08-17 | 2020-08-23
14 | Development | Payments | Review | Review | PL | P-PS | 2020-08-17 | 2020-08-23
15 | Development | Contact Us | Coding | Core work | TM | P-CU | 2020-08-17 | 2020-08-23
16 | Development | Contact Us | Review | Review | PL | P-CU | 2020-08-17 | 2020-08-23
17 | Development | Chat-Bot | Coding | Core work | TM | P-CB | 2020-08-17 | 2020-08-23
18 | Development | Chat-Bot | Review | Review | PL | P-CB | 2020-08-17 | 2020-08-23
19 | Development | Nav-Bar | Coding | Core work | TM | P-NB | 2020-08-17 | 2020-08-23
20 | Development | Nav-Bar | Review | Review | PL | P-NB | 2020-08-17 | 2020-08-23
21 | Development | Footer | Coding | Core work | TM | P-FT | 2020-08-17 | 2020-08-23
22 | Development | Footer | Review | Review | PL | P-FT | 2020-08-17 | 2020-08-23
23 | Development | Database Management of G-Forms input | Coding | Core work | TM | P-DG | 2020-08-17 | 2020-08-23
24 | Development | Database Management of G-Forms input | Review | Review | PL | P-DG | 2020-08-17 | 2020-08-23
25 | Development | Database Management Of Payment Details | Coding | Core work | TM | P-DP | 2020-08-17 | 2020-08-23
26 | Development | Database Management Of Payment Details | Review | Review | PL | P-DP | 2020-08-17 | 2020-08-23
27 | Development | Miscellaneous Database Management | Coding | Core work | TM | P-MM | 2020-08-17 | 2020-08-23
28 | Development | Miscellaneous Database Management | Review | Review | PL | P-MM | 2020-08-17 | 2020-08-23
29 | Testing | Home Page | Unit Testing | Core work | TM | P-HP | 2020-08-24 | 2020-08-30
30 | Testing | Home Page | Review | Review | PL | P-HP | 2020-08-24 | 2020-08-30
31 | Testing | About Us | Unit Testing | Core work | TM | P-AU | 2020-08-24 | 2020-08-30
32 | Testing | About Us | Review | Review | PL | P-AU | 2020-08-24 | 2020-08-30
33 | Testing | Our Services | Unit Testing | Core work | TM | P-OS | 2020-08-24 | 2020-08-30
34 | Testing | Our Services | Review | Review | PL | P-OS | 2020-08-24 | 2020-08-30
35 | Testing | Payments | Unit Testing | Core work | TM | P-PS | 2020-08-24 | 2020-08-30
36 | Testing | Payments | Review | Review | PL | P-PS | 2020-08-24 | 2020-08-30
37 | Testing | Contact Us | Unit Testing | Core work | TM | P-CU | 2020-08-24 | 2020-08-30
38 | Testing | Contact Us | Review | Review | PL | P-CU | 2020-08-24 | 2020-08-30
39 | Testing | Chat-Bot | Unit Testing | Core work | TM | P-CB | 2020-08-24 | 2020-08-30
40 | Testing | Chat-Bot | Review | Review | PL | P-CB | 2020-08-24 | 2020-08-30
41 | Testing | Nav-Bar | Unit Testing | Core work | TM | P-NB | 2020-08-24 | 2020-08-30
42 | Testing | Nav-Bar | Review | Review | PL | P-NB | 2020-08-24 | 2020-08-30
43 | Testing | Footer | Unit Testing | Core work | TM | P-FT | 2020-08-24 | 2020-08-30
44 | Testing | Footer | Review | Review | PL | P-FT | 2020-08-24 | 2020-08-30
45 | Testing | Database Management of G-Forms input | Unit Testing | Core work | TM | P-DG | 2020-08-24 | 2020-08-30
46 | Testing | Database Management of G-Forms input | Review | Review | PL | P-DG | 2020-08-24 | 2020-08-30
47 | Testing | Database Management Of Payment Details | Unit Testing | Core work | TM | P-DP | 2020-08-24 | 2020-08-30
48 | Testing | Database Management Of Payment Details | Review | Review | PL | P-DP | 2020-08-24 | 2020-08-30
49 | Testing | Miscellaneous Database Management | Unit Testing | Core work | TM | P-MM | 2020-08-24 | 2020-08-30
50 | Testing | Miscellaneous Database Management | Review | Review | PL | P-MM | 2020-08-24 | 2020-08-30
51 | Testing | Integerated Modules | Integration testing | Core work | TM | P-IM-IT | 2020-08-24 | 2020-08-30
52 | Testing | Integerated Modules | Review | Review | PL | P-IM-IT | 2020-08-24 | 2020-08-30
53 | Testing | Integerated Modules | System Testing | Core work | TM | P-IM-ST | 2020-08-24 | 2020-08-30
54 | Testing | Integerated Modules | Review | Review | PL | P-IM-ST | 2020-08-24 | 2020-08-30
55 | Testing | Integerated Modules | Acceptance Testing | Core work | TM | P-IM-AT | 2020-08-24 | 2020-08-30
56 | Testing | Integerated Modules | Review | Review | PL | P-IM-AT | 2020-08-24 | 2020-08-30
57 | Application | Integerated Modules | Publishing site and setting up the database. | Core work | TM | P-IM-PL | 2020-08-31 | 2020-09-06
58 | Application | Integerated Modules | Review | Review | PL | P-IM-PL | 2020-08-31 | 2020-09-06
59 | Maintainance | Integerated Modules | Maintainace of the site | Core work | TM | P-IM-MC | 2020-09-06 | Last date of contract
60 | Maintainance | Integerated Modules | Review | Review | PL | P-IM-MC | 2020-09-06
Note on B5: Running serial Number
Note on C5: PDLC Stage Name e.g. Requirement, Design, Coding, Testing, etc.
Note on D5: Module Name
Note on E5: Individual Work Item / Review item for the PDLC Stage and Module. E.g. Report Design, Screen Design, Function to be coded
Note on F5: Work allocation Review Rework Re-review
Note on G5: PL, Team Member to whom the work / review item is assigned
Note on H5: Reference file ID / Bug ID for Review, Rework, Re-review
Note on I5: Planned start date for the work item
Note on J5: Planned end date for the Work Item
Note on K5: Actual Start date
Note on L5: Actual end date for the work item
Note on M5: Planned Effort for the work item in Hrs
Note on N5: Actual Effort for the work item in Hrs
Note on O5: Number of resources allocated for the work item
Note on P5: Planned, Started, Completed, Postponed, Cancelled, Transferred (when the work item is transferred from one resource to another. In this case retain the first allocation entry with Transferred status with Actual End Date showing transfer date. Add new entry for showing new resource name and new planned date.
Note on Q5: Mention the serial nos. Of work items whose completion is prerequisite for this work item.
Note on R5: Explanatory Text, if required, for the entry