## Slide 1: Unit 2
Project Scheduling

## Slide 2: PERT
PERT is a management technique used with responsibility accounting and to attain well defined objectives.
It is designed for scheduling complex interrelated tasks of the projects.
PERT System of Three Time Estimate
  Optimistic Time
  Most likely Time (tm)
  Pessimistic Time (tp)

## Slide 3
PERT Algorithm
  Develop a list of activities that made up the project including immediate predecessors.
  For each activity, a rough PERT network is drawn on the basis of which activity precedes, which activity follows which one, which activity are concurrent with which one.
  The network is sketched to conform to rules and conventions.
  Events are numbered in ascending order from left to right.
  Time estimates (Optimistic Estimate, Most Likely Estimate, Pessimistic Estimate)for each activity are obtained.
  Then upon the assumption of beta distribution for the activity duration, the expected time te for each activity is computed using te = 1(1+4m+b)/6.

## Slide 4
PERT Algorithm…(continued)
  Using the expected activity time estimates, determine the earliest start time and the earliest finish time for each activity, the earliest finish time for the complete project corresponds to the earliest finish time for the last activity.
  After determining the latest start time and the latest finish time for each activity, compute the float associated with each activity, the critical path activities are the activities with zero float. Determine now the critical path through the given network.
  Using the values for b and a, which were determined in step 5. calculate the variance (σ2) of each activities time estimated by σ2 = [1(b-a)/6] 2.
  Use the variability in the activity times to estimate the variability of the project completion date, then using this estimate compute the probability of meeting a specified completion date by using the standard normal equation
  Z = Due date – Expected date of completion
  √ Project Variance
  where Z = no of standard deviations the due date or target date lies from the mean or expected date

## Slide 5: CPM
CPM method is developed by E. I. du Pont de Nemours Company (USA) in 1958.
It is used to schedule and control the project.
It is used to estimate the total project duration and to assign starting and finishing times to all activities involved in the project.
CPM Systems
  Activity-On-Arrow (AOA) Network
  Activity-On-Node (AON) Network

## Slide 6
Steps
  Break down the project into various activities systematically. Label all activities. Arrange all the activities in logical sequence. Construct the network diagram.
  Number all the nodes (events) and activities. Find the time for each activity considering it to be deterministic. Indicate the activity times on the arrow diagram.
  Calculate earliest start time, earliest finish time, latest start time and latest finish time. Tabulate activity normal times, earliest times and latest times.
  Determine the total float for each activity by taking difference between the earliest time and latest time for each node.
  Identify the critical activities and connect them with the beginning node and the ending node in the network diagram by double line arrow. This gives the critical path.
  Calculates the total project duration.
  Reduce the total project duration, crash the critical activities of the network.
  Optimize the cost.
  Update the network and smooth the network resource.

## Slide 7: Problems on PERT (Program Evaluation & Review Technique) & CPM (Critical Path Method)

## Slide 8: PERT
Problem 1: A small project consisting of eight activities has the given characteristics:
Draw the PERT network for the project.
Prepare the activity schedule for the project.
Determine the critical path.

## Slide 9: PERT
Activity | Preceding Activity | Optimistic Time | Most Likely Time | Pessimestic Time
A | None | 2 | 4 | 12
B | None | 10 | 12 | 26
C | A | 8 | 9 | 10
D | A | 10 | 15 | 20
E | A | 7 | 7.5 | 11
F | B, C | 9 | 9 | 9
G | D | 3 | 3.5 | 7
H | E, F, G | 5 | 5 | 5

## Slide 10: PERT
Draw the PERT network for the project.
A
F
G
C
E
B
D
H

## Slide 11: PERT
2. Prepare the activity schedule for the project.
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time te = a+4m+b 6 | Variance σ2t = ((b-a)/6)2
A | None | 2 | 4 | 12 |  | 
B | None | 10 | 12 | 26 |  | 
C | A | 8 | 9 | 10 |  | 
D | A | 10 | 15 | 20 |  | 
E | A | 7 | 7.5 | 11 |  | 
F | B, C | 9 | 9 | 9 |  | 
G | D | 3 | 3.5 | 7 |  | 
H | E, F, G | 5 | 5 | 5 |  | 

## Slide 12: PERT
2. Prepare the activity schedule for the project.
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time te = a+4m+b 6 | Variance σ2t = ((b-a)/6)2
A | None | 2 | 4 | 12 | 5 | 25/9
B | None | 10 | 12 | 26 | 14 | 64/9
C | A | 8 | 9 | 10 | 9 | 1/9
D | A | 10 | 15 | 20 | 15 | 25/9
E | A | 7 | 7.5 | 11 | 8 | 4/9
F | B, C | 9 | 9 | 9 | 9 | 0
G | D | 3 | 3.5 | 7 | 4 | 4/9
H | E, F, G | 5 | 5 | 5 | 5 | 0

## Slide 13: PERT
0
A 5
F 9
G 4
C 9
E 8
B 14
D 15
H 5
ET
LT

## Slide 14: PERT
0
A 5
F 9
G 4
C 9
E 8
B 14
D 15
H 5
ET
LT
0
24
14
20
5
29

## Slide 15: PERT
0
A 5
F 9
G 4
C 9
E 8
B 14
D 15
H 5
ET
LT
0 0
24 24
14 15
20 20
5 5
29 29

## Slide 16: PERT
0
A 5
F 9
G 4
C 9
E 8
B 14
D 15
H 5
ET
LT
0 0
24 24
14 15
20 20
5 5
29 29

## Slide 17: PERT
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | EFT | LST | LFT
A | None | 2 | 4 | 12 | 5 | 25/9 |  |  |  | 
B | None | 10 | 12 | 26 | 14 | 64/9 |  |  |  | 
C | A | 8 | 9 | 10 | 9 | 1/9 |  |  |  | 
D | A | 10 | 15 | 20 | 15 | 25/9 |  |  |  | 
E | A | 7 | 7.5 | 11 | 8 | 4/9 |  |  |  | 
F | B, C | 9 | 9 | 9 | 9 | 0 |  |  |  | 
G | D | 3 | 3.5 | 7 | 4 | 4/9 |  |  |  | 
H | E, F, G | 5 | 5 | 5 | 5 | 0 |  |  |  | 

## Slide 18: PERT
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | EFT | LST | LFT
A | None | 2 | 4 | 12 | 5 | 25/9 | 0 | 5 |  | 
B | None | 10 | 12 | 26 | 14 | 64/9 | 0 | 14 |  | 
C | A | 8 | 9 | 10 | 9 | 1/9 | 5 | 14 |  | 
D | A | 10 | 15 | 20 | 15 | 25/9 | 5 | 20 |  | 
E | A | 7 | 7.5 | 11 | 8 | 4/9 | 5 | 13 |  | 
F | B, C | 9 | 9 | 9 | 9 | 0 | 14 | 23 |  | 
G | D | 3 | 3.5 | 7 | 4 | 4/9 | 20 | 24 |  | 
H | E, F, G | 5 | 5 | 5 | 5 | 0 | 24 | 29 |  | 

## Slide 19: PERT
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | ENT | LST | LET
A | None | 2 | 4 | 12 | 5 | 25/9 | 0 | 5 |  | 5
B | None | 10 | 12 | 26 | 14 | 64/9 | 0 | 14 |  | 15
C | A | 8 | 9 | 10 | 9 | 1/9 | 5 | 14 |  | 15
D | A | 10 | 15 | 20 | 15 | 25/9 | 5 | 20 |  | 20
E | A | 7 | 7.5 | 11 | 8 | 4/9 | 5 | 13 |  | 24
F | B, C | 9 | 9 | 9 | 9 | 0 | 14 | 23 |  | 24
G | D | 3 | 3.5 | 7 | 4 | 4/9 | 20 | 24 |  | 24
H | E, F, G | 5 | 5 | 5 | 5 | 0 | 24 | 29 |  | 29

## Slide 20: PERT
Activity | Preceding Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | EFT | LST | LFT
A | None | 2 | 4 | 12 | 5 | 25/9 | 0 | 5 | 0 | 5
B | None | 10 | 12 | 26 | 14 | 64/9 | 0 | 14 | 1 | 15
C | A | 8 | 9 | 10 | 9 | 1/9 | 5 | 14 | 6 | 15
D | A | 10 | 15 | 20 | 15 | 25/9 | 5 | 20 | 5 | 20
E | A | 7 | 7.5 | 11 | 8 | 4/9 | 5 | 13 | 16 | 24
F | B, C | 9 | 9 | 9 | 9 | 0 | 14 | 23 | 15 | 24
G | D | 3 | 3.5 | 7 | 4 | 4/9 | 20 | 24 | 20 | 24
H | E, F, G | 5 | 5 | 5 | 5 | 0 | 24 | 29 | 24 | 29

## Slide 21: PERT
Critical Path:
A - D - G - H = 5+15+4+5 = 29
A - E – H = 5+8+5 = 18
Therefore, Project Completion Time = 29 weeks
Project Variance = 25/9 + 25/9 +4/9 + 0 = 6

## Slide 22: PERT
Problem 2: A small project consisting of eight activities has the given characteristics:
Draw the PERT network for the project.
Prepare the activity schedule for the project.
Determine the critical path.

## Slide 23: PERT
Preceding Activity | Activity | Optimistic Time | Most Likely Time | Pessimestic Time
1 | 2 | 6 | 9 | 12
1 | 3 | 3 | 4 | 11
2 | 4 | 2 | 5 | 14
3 | 4 | 4 | 6 | 8
3 | 5 | 1 | 1.5 | 5
2 | 6 | 5 | 6 | 7
4 | 6 | 7 | 8 | 15
5 | 6 | 1 | 2 | 3

## Slide 24: PERT
Draw the PERT network for the project.
1
5
6
3
2
4

## Slide 25: PERT
2. Prepare the activity schedule for the project.
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time te = a+4m+b 6 | Variance σ2t = ((b-a)/6)2
1 | 2 | 6 | 9 | 12 |  | 
1 | 3 | 3 | 4 | 11 |  | 
2 | 4 | 2 | 5 | 14 |  | 
3 | 4 | 4 | 6 | 8 |  | 
3 | 5 | 1 | 1.5 | 5 |  | 
2 | 6 | 5 | 6 | 7 |  | 
4 | 6 | 7 | 8 | 15 |  | 
5 | 6 | 1 | 2 | 3 |  | 

## Slide 26: PERT
2. Prepare the activity schedule for the project.
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time te = a+4m+b 6 | Variance σ2t = ((b-a)/6)2
1 | 2 | 6 | 9 | 12 | 9 | 1
1 | 3 | 3 | 4 | 11 | 5 | 16/9
2 | 4 | 2 | 5 | 14 | 6 | 4
3 | 4 | 4 | 6 | 8 | 6 | 4/9
3 | 5 | 1 | 1.5 | 5 | 2 | 4/9
2 | 6 | 5 | 6 | 7 | 6 | 1/9
4 | 6 | 7 | 8 | 15 | 9 | 16/9
5 | 6 | 1 | 2 | 3 | 2 | 1/9

## Slide 27: PERT
Draw the PERT network for the project.
1
5
6
3
2
4
ET
LT
9
6
6
9
5
6
2
2

## Slide 28: PERT
Draw the PERT network for the project.
1
5
6
3
2
4
ET
LT
9
6
6
9
5
6
2
2
0
9
5
15
7
24

## Slide 29: PERT
Draw the PERT network for the project.
1
5
6
3
2
4
ET
LT
9
6
6
9
5
6
2
2
0 0
9 9
5 9
15 15
7 22
24 24

## Slide 30: PERT
Draw the PERT network for the project.
1
5
6
3
2
4
ET
LT
9
6
6
9
5
6
2
2
0 0
9 9
5 9
15 15
7 22
24 24

## Slide 31: PERT
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | ENT | LST | LET
1 | 2 | 6 | 9 | 12 | 9 | 1 |  |  |  | 
1 | 3 | 3 | 4 | 11 | 5 | 16/9 |  |  |  | 
2 | 4 | 2 | 5 | 14 | 6 | 4 |  |  |  | 
3 | 4 | 4 | 6 | 8 | 6 | 4/9 |  |  |  | 
3 | 5 | 1 | 1.5 | 5 | 2 | 4/9 |  |  |  | 
2 | 6 | 5 | 6 | 7 | 6 | 1/9 |  |  |  | 
4 | 6 | 7 | 8 | 15 | 9 | 16/9 |  |  |  | 
5 | 6 | 1 | 2 | 3 | 2 | 1/9 |  |  |  | 

## Slide 32: PERT
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | ENT | LST | LET
1 | 2 | 6 | 9 | 12 | 9 | 1 | 0 | 9 |  | 
1 | 3 | 3 | 4 | 11 | 5 | 16/9 | 0 | 5 |  | 
2 | 4 | 2 | 5 | 14 | 6 | 4 | 9 | 15 |  | 
3 | 4 | 4 | 6 | 8 | 6 | 4/9 | 5 | 11 |  | 
3 | 5 | 1 | 1.5 | 5 | 2 | 4/9 | 5 | 7 |  | 
2 | 6 | 5 | 6 | 7 | 6 | 1/9 | 9 | 15 |  | 
4 | 6 | 7 | 8 | 15 | 9 | 16/9 | 15 | 24 |  | 
5 | 6 | 1 | 2 | 3 | 2 | 1/9 | 7 | 9 |  | 

## Slide 33: PERT
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | ENT | LST | LET
1 | 2 | 6 | 9 | 12 | 9 | 1 | 0 | 9 |  | 9
1 | 3 | 3 | 4 | 11 | 5 | 16/9 | 0 | 5 |  | 9
2 | 4 | 2 | 5 | 14 | 6 | 4 | 9 | 15 |  | 15
3 | 4 | 4 | 6 | 8 | 6 | 4/9 | 5 | 11 |  | 15
3 | 5 | 1 | 1.5 | 5 | 2 | 4/9 | 5 | 7 |  | 22
2 | 6 | 5 | 6 | 7 | 6 | 1/9 | 9 | 15 |  | 24
4 | 6 | 7 | 8 | 15 | 9 | 16/9 | 15 | 24 |  | 24
5 | 6 | 1 | 2 | 3 | 2 | 1/9 | 7 | 9 |  | 24

## Slide 34: PERT
Preceding Activity | Activity | Optimistic Time (a) | Most Likely Time (m) | Pessimestic Time (b) | Expected Time Te | Variance σ2t | EST | EFT | LST | LFT
1 | 2 | 6 | 9 | 12 | 9 | 1 | 0 | 9 | 0 | 9
1 | 3 | 3 | 4 | 11 | 5 | 16/9 | 0 | 5 | 4 | 9
2 | 4 | 2 | 5 | 14 | 6 | 4 | 9 | 15 | 9 | 15
3 | 4 | 4 | 6 | 8 | 6 | 4/9 | 5 | 11 | 9 | 15
3 | 5 | 1 | 1.5 | 5 | 2 | 4/9 | 5 | 7 | 20 | 22
2 | 6 | 5 | 6 | 7 | 6 | 1/9 | 9 | 15 | 18 | 24
4 | 6 | 7 | 8 | 15 | 9 | 16/9 | 15 | 24 | 15 | 24
5 | 6 | 1 | 2 | 3 | 2 | 1/9 | 7 | 9 | 22 | 24

## Slide 35: PERT
Critical Path:
1-2-4-6
Therefore, Project Completion Time = 24 days
Project Variance = 1+4+16/9= 6.78

## Slide 36: A small project consisting of eight activities has the following characteristics:

## Slide 37
(i) Draw the PERT network for the project.
(ii) Prepare the activity schedule for the project.
(iii) Determine the critical path.

## Slide 38: Thank you